## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18355 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme under Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte. (Part-C) | Assistant Engineer(Civil) |  | ORD/000103/2023-2024 | 1034/SWSD | 26/07/2023 | 09/09/2023 | ROYAL ENTERPRISE | 10.03 | 0 | 0 | 0
2 | JALPAIGURI |  | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18355 | Augmentation | Laying distribution system, rising main, construction of pump house and tubewells along with other allied works inconnection with Jal Jeevan Mission of Augmentation PURBA PASCHIM DHANTALA Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000106/2023-2024 | 1140/SWSD | 07/08/2023 | 04/01/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 181.57 | 0 | 0 | 0
3 | JALPAIGURI |  | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18355 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme under Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte. (Part-B) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000123/2023-2024 | 1232/SWSD | 14/08/2023 | 13/09/2023 | SHREYANSH AUTOMOBILE | 4.95 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18355 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PURBA PASCHIM DHANTALA (ZONE-II and III) PWSS, ZONE-II, TW No I,II AND ZONE-III,TW NO- I in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000670/2023-2024 | 1485/NMD | 17/08/2023 | 16/09/2023 | SARKAR ELECTRIC | 34.22 | 28.26 | 82.57 | 70
5 | JALPAIGURI |  | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18355 | Augmentation | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme under Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte. (Part-A) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000140/2023-2024 | 1413/SWSD | 22/08/2023 | 21/09/2023 | SANJAY KUMAR BHADRA | 4.95 | 0 | 0 | 0
6 | JALPAIGURI |  | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18355 | Augmentation | Laying distribution system, rising main, construction of pump house and boundary wall, installation of Iron Elimination Plant, repairing of OHR, pump house and boundary wall, sinking of tubewell along with other allied works in connection with Jal Jeevan Mission Programme for Augmentation of PURBA PASCHIM DHANTALA Piped Water Supply Scheme (Zone-I) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000132/2023-2024 | 1367/SWSD | 18/08/2023 | 14/04/2024 | UNIBRO INFRASERV PRIVATE LIMITED | 549.31 | 0 | 0 | 0
7 | JALPAIGURI |  | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18355 | Augmentation | Providing Functional Household Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme for Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-I) at Rajganj Block Under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000200/2023-2024 | 2049/SWSD | 07/11/2023 | 22/12/2023 | S.G.CONSTRUCTION | 11.87 | 0 | 0 | 0
8 | JALPAIGURI |  | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18355 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000087/2022-2023 | 2213/SWSD | 05/01/2023 | 05/01/2023 | Resource Division | 76.69 | 0 | 0 | 0
9 | JALPAIGURI |  | Siliguri W/S Division | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18355 | Augmentation | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF PURBA PASCHIM DHANTALA PIPED WATER SUPPLY SCHEME UNDER RAJGANJ BLOCK, JALPAIGURI DISTRICT UNDER SILIGURI W/S DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000070/2023-2024 | 263/SSD | 05/06/2023 | 15/06/2023 | ENVIROTECH SOLUTIONS | 3.6 | 0 | 0 | 30
10 | JALPAIGURI |  | Northern Mechanical | AUGMENTATION OF PURBA PASCHIM DHANTALA(ZONE-I, II & III) PIPED WATER SUPPLY SCHEME | SM/18355 | Augmentation | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 06/05/2025 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0 | 0
Total | [13 empty] | 922.72 | 28.26 | 3.06