## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF BOALMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15605 |  | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000775/2023-2024 | 1631/NMD | 27/09/2023 | 25/01/2024 | A.K. INDUSTRIES | 206.06 | 0 | 0 | 55
2 | JALPAIGURI |  | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF BOALMARI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15605 |  | Supplying and Installation of Display Boards at BOALMARI and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000166/2024-2025 | 1215/HQ/NMD | 15/07/2024 | 30/07/2024 | GURUKUL INFOTECH | 2.93 | 0 | 0 | 0
Total | [13 empty] | 208.99 | 0 | 0