## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHALSA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15610 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Arji Maria Kamala Pukhari and Others PWSS in the Jalpaiguri District under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000775/2023-2024 | 1631/NMD | 27/09/2023 | 29/01/2026 | A.K. INDUSTRIES | 206.06 | 5.8 | 2.81 | 93
2 | JALPAIGURI |  | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHALSA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15610 | Solarisation | Supplying and Installation of Display Boards at Baikur PWSS and other adjacent different piped water supply schemes in connection with Jal Jeevan Mission under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000165/2024-2025 | 1214/HQ/NMD | 15/07/2024 | 30/07/2024 | SARKAR ELECTRIC | 4.11 | 0.2 | 4.76 | 100
3 | JALPAIGURI |  | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHALSA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15610 | Solarisation | Quotation charges for net metering connection at Chalsa PWSS in the dist. of Jalpaiguri under NMD, PHE, Dte Consumer id-402479786 Application no-4003605307 |  |  | BILL/02743/2024-2025 | BP/24-25/274 | 28/03/2025 | 28/03/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
4 | JALPAIGURI |  | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT REJUVENATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHALSA UNDER JALPAIGURI DISTRICT UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15610 | Solarisation | Solar quotation charges for Chalsa T/W ¿III , NMD ,PHE DTE. Application no. - 4003605307 Consumer I.D- 402479786 |  |  | BILL/00350/2026-2027 |  | 13/05/2026 | 13/05/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.18 | 0 | 0 | 0
Total | [13 empty] | 210.36 | 5.99 | 2.85