## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | om lab |  |  | VCH/001744/2021-2022 | 410 | 24/03/2022 |  | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.77 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | chemical on nabl |  |  | VCH/001732/2021-2022 | 415 | 25/03/2022 |  | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.88 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | lab |  |  | VCH/001733/2021-2022 | 416 | 25/03/2022 |  | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.88 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | sitalkuchi lab |  |  | VCH/001734/2021-2022 | 417 | 25/03/2022 |  | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.7 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | nabl lab |  |  | VCH/001745/2021-2022 | 391 | 21/03/2022 |  | LAB SOLUTION | 3.76 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | Running of water testing Laboratory at Mathabhanga sub Division office Campus for physical, Chemical & bacteriology test of water sample from 01/08/22 to 30/09/22 under COB Division PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000408/2022-2023 | 207/RWS | 29/07/2022 | 31/07/2022 | BIJOY ROY | 0.98 | 0.98 | 100 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | Repairing cum Orientation of Nishiganj Labortary at Mathabhanga in-connection with implementation of JJM programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000304/2022-2023 | 913/CD | 26/09/2022 | 26/10/2022 | SANJAY MANDAL | 6.97 | 6.93 | 99.46 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | Procurement of Chemicals Glassware & consumables for Mekhliganj Sub-District Water testing Laboratories | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000312/2022-2023 | 921/CD | 26/09/2022 | 26/10/2022 | DULAL MAJUMDER | 3.13 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | Procurement of Chemicals Glassware & consumables for Mathabhanga Sub-District Water testing Laboratories. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000313/2022-2023 | 922/CD | 26/09/2022 | 26/10/2022 | DULAL MAJUMDER | 4.25 | 4.25 | 100 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | Procurement of Chemicals Glassware & consumables for COB District Water testing Laboratories | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000309/2022-2023 | 918/CD | 26/09/2022 | 26/10/2022 | DULAL MAJUMDER | 4.16 | 4.16 | 100 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | SALRY PAYMENT OF 10 NOS. LABOHRATORY STAFF |  |  | BILL/00549/2023-2024 | BP-40-52 | 19/04/2023 |  | SECRETARY BOYS RECREATION CLUB DINHATA | 4.85 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Procurement of Chemicals & Consumables, Glassware etc. and Annual O & M of water testing laboratories . | SM/06622 | Support-WQMSP | HIRING VEHICLE |  |  | BILL/00489/2024-2025 | null | 01/06/2024 |  | ANIMESH DHAR CHOUDHURY | 0.36 | 0 | 0 | 0
Total | [13 empty] | 44.7 | 16.32 | 36.5