## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Nakkatigachhi & Adjoining Mouzas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07148 | Retrofitting | Providing F.H.T.C & other allied work related to Pipe Line in the Command area at NAKKATIGACHHI PWSS under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000152/2020-2021 | 1424/CD | 08/01/2021 | 08/04/2021 | ASHIM KUMAR CHAKRABORTY | 60.57 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Nakkatigachhi & Adjoining Mouzas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07148 | Retrofitting | Providing House connection for NAKKATIGACHI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000346/2021-2022 | 1247/CD | 09/02/2022 | 01/03/2022 | ASHIM KUMAR CHAKRABORTY | 8.77 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Nakkatigachhi & Adjoining Mouzas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07148 | Retrofitting | FHTC |  |  | VCH/001221/2021-2022 | BP-2021-22-352 | 25/01/2022 | 25/01/2022 | MS BIDYUT SARKAR | 49.69 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Nakkatigachhi & Adjoining Mouzas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07148 | Retrofitting | FHTC |  |  | VCH/001606/2021-2022 | BP_2021_22_430 | 10/03/2022 | 10/03/2022 | RAJIB CHAKRABORTY | 4.67 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Nakkatigachhi & Adjoining Mouzas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07148 | Retrofitting | COST OF PIPES |  |  | VCH/001746/2021-2022 | BP-2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 24.36 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Nakkatigachhi & Adjoining Mouzas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07148 | Retrofitting | fhtc |  |  | VCH/001373/2021-2022 | BP-2021-22-393 | 22/02/2022 | 22/02/2022 | MODAN MOHAN UNEMPLOYED CO-OP LABOUR | 7.73 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Nakkatigachhi & Adjoining Mouzas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07148 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000054/2021-2022 | 1199/CD | 01/02/2022 | 01/02/2022 | Resource Division | 2.06 | 0 | 0 | 0
Total | [13 empty] | 157.85 | 0 | 0