## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | Providing F.H.T.C & other allied work related to pipe line in the command area at Alokjhari PWSS under Cooch Behar Division, PHED. |  |  | VCH/000140/2021-2022 |  | 28/04/2021 | 28/04/2021 | TAPAN CHANDA | 33.26 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | fhtc |  |  | VCH/001027/2021-2022 | BP-2021-22-218 | 11/10/2021 | 11/10/2021 | SANJAY MANDAL | 5 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | fhtc alokjari |  |  | VCH/000548/2021-2022 | BP-2021-22-85 | 20/07/2021 | 20/07/2021 | TAPAN CHANDA | 33.26 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | FHTC ALOKJARI |  |  | VCH/000670/2021-2022 | BP-2021-22-85 | 27/07/2021 | 27/07/2021 | TAPAN CHANDA | 33.26 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | Providing Functionqal household tap connection (Unmetered) 125 nos in Alokjhari Piped Water Supply Scheme under Cooch Behar Division, P.H.E Dte. under Jaldhara Programme |  |  | VCH/000807/2021-2022 |  | 08/10/2021 | 08/10/2021 | KRISHNA GOPAL BASK | 5 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | fhtc |  |  | VCH/001134/2021-2022 | BP-2021-22-319 | 09/12/2021 | 09/12/2021 | MS BIDYUT SARKAR | 3.73 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | fhtc alokjhari |  |  | VCH/001127/2021-2022 | BP-2021-22-323 | 09/12/2021 | 09/12/2021 | TAPAN CHANDA | 20.29 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | fhtc |  |  | VCH/000232/2022-2023 | BP_83_22_23 | 10/06/2022 | 10/06/2022 | KRISHNA GOPAL BASK | 5.44 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | FHTC |  |  | VCH/000147/2022-2023 | BP-22-23-62 | 05/05/2022 | 05/05/2022 | MATARA CONSTRUCTION CO. | 10 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | DIFF. WATER FACILITY AT ALOKJHARI |  |  | VCH/000190/2022-2023 | BP_83_22_23 | 10/06/2022 | 10/06/2022 | KRISHNA GOPAL BASK | 7.06 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Alokjhari Piped Water Suply Scheme | SM/07156 | Retrofitting | Providing House connection for ALOKJHARI PWSS under Cooch Behar Division. PHE Dte | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000257/2022-2023 | 741/CD | 27/08/2022 | 11/10/2022 | KISHORE BOSE | 8.28 | 0 | 0 | 1
Total | [13 empty] | 164.58 | 0 | 0