## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | fhtc |  |  | VCH/001008/2021-2022 | BP-2021-22-268 | 30/10/2021 | 30/10/2021 | GHOSH AND SAHA CONSTRUCTION | 20.14 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | FHTC AT KONACHATRA |  |  | VCH/000922/2021-2022 | BP-2021-22-188 | 11/10/2021 | 11/10/2021 | ASHIM KUMAR CHAKRABORTY | 42.48 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | PROVIDING FHTC UNDER KONACHATRA PWSS ( P-B) |  |  | VCH/000745/2021-2022 |  | 30/09/2021 | 30/09/2021 | SIDHARTHA ROY | 28.26 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | FHTC AT Konachatra Piped Water Suply Scheme |  |  | VCH/000995/2021-2022 | BP-2021-22-277 | 30/10/2021 | 30/10/2021 | SANJAY MANDAL | 5.06 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | PROVIDING FHTC UNDER OF KONACHATRA PWSS PART- C |  |  | VCH/000751/2021-2022 |  | 30/09/2021 | 30/09/2021 | BISWAJIT GUHA | 27.44 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | FHTC |  |  | VCH/000978/2021-2022 | BP-2021-22-257 | 30/10/2021 | 30/10/2021 | MATARA CONSTRUCTION CO. | 12.17 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | fhtc |  |  | VCH/001021/2021-2022 | BP-2021-22-258 | 30/10/2021 | 30/10/2021 | MS BIDYUT SARKAR | 4.99 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | Providing functional House hold tap connection(Unmetered)125 Nos in Lauchapra ( Zone-I ) Piped water Supply Scheme under Cooch Behar Division, P.H.E. Dte. under Jaldhara Programme. |  |  | VCH/000161/2021-2022 |  | 28/05/2021 | 28/05/2021 | SOUMITRA BANERJEE | 4.87 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | FHTC KUMIRGHAY |  |  | VCH/000620/2021-2022 | BP-2021-22-149 | 17/08/2021 | 17/08/2021 | ANIMESH DHAR CHOUDHURY | 0.13 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | FHTC TUTIER KUTHI |  |  | VCH/000586/2021-2022 | BP-2021-22-92 | 28/07/2021 | 28/07/2021 | SOUMITRA BANERJEE | 4.7 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | Providing F.H.T.C & other allied work related to pipeline in the command area at Konachatra PWSS under Cooch Behar Division, PHED (PART-A) |  |  | VCH/000776/2021-2022 |  | 01/10/2021 | 01/10/2021 | RELIANCE UN EMPLOYED ENGINEERS CO OP SOC LTD | 29.28 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | cost metaral |  |  | VCH/001181/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.17 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | Constructions of 3.6 mX 3.0 m Switch room & boundary wall, Providing FHTC, New laying of UPVC/DI Pipe Line & Other allied works at Satbhandari (Part-A) PWSS under Cooch Behar Division, P.H.E Dte. | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000369/2021-2022 | 1272/CD | 09/02/2022 | 10/04/2022 | SWAPAN KR.SARKAR | 59.6 | 0 | 0 | 90
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Konachatra Piped Water Suply Scheme | SM/07158 | Retrofitting | Providing FHTC Repairing of Pump house & other allied works at KONACHATRA PWSS under JAL JEEVAN MISSION | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000343/2022-2023 | 996/CD | 29/09/2022 | 29/10/2022 | KRISHCHAK TRADING PRIVATE LIMITED | 6.28 | 0 | 0 | 100
Total | [13 empty] | 245.56 | 0 | 0