## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | FHTC AT MATIKATA |  |  | VCH/000982/2021-2022 | BP-2021-22-261 | 30/10/2021 | 30/10/2021 | NABIN DEBNATH | 10.14 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | fhtc cahkier chahra |  |  | VCH/000558/2021-2022 | BP-2021-22-80 | 27/07/2021 | 27/07/2021 | CHAKRABORTY ENTERPRISE. | 5.01 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | FHTC CHAKCKA |  |  | VCH/000856/2021-2022 | BP-2021_22_88 | 28/07/2021 | 28/07/2021 | M/S. MANDAL CONSTRUCTION | 0 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | EXTENSION WORK ORDER FOR Providing Functional Household tap connection(Unmetered)125 Nos. in PUTIA BAROMASIA Piped Water Supply Scheme under Cooch Behar Division, P.H.E Dte. under Jaldhara Programme |  |  | VCH/000132/2021-2022 |  | 21/04/2021 | 21/04/2021 | NABIN DEBNATH | 5.04 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | FHTC BARA SOULMARI |  |  | VCH/000500/2021-2022 | BP-2021_22_45 | 27/07/2021 | 27/07/2021 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 5.01 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | fhtc putia bara masia |  |  | VCH/000552/2021-2022 | BP-2021-22-119 | 04/08/2021 | 04/08/2021 | NABIN DEBNATH | 5.04 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | Providing house connection of drinking water to the household of command area under Matikata W/S Scheme ( Part-B) of Cooch Behar Division, P..H.E. Dte. under Jaldhara programme |  |  | VCH/000122/2021-2022 |  | 20/04/2021 | 20/04/2021 | ANIMESH DHAR CHOUDHURY | 4.89 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | PRO FHTC TO THE HH OF COMMAND MATIKATA PWSS |  |  | VCH/000249/2021-2022 |  | 07/06/2021 | 07/06/2021 | SIRTHATHA ROY | 21.23 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | FHTC AT MATIKATA |  |  | VCH/000525/2021-2022 | BP-2021-22-110 | 28/07/2021 | 28/07/2021 | ANIMESH DHAR CHOUDHURY | 4.89 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | FHTC AT MATIKATA |  |  | VCH/000948/2021-2022 | BP-2021-22-226 | 11/10/2021 | 11/10/2021 | ANIMESH DHAR CHOUDHURY | 12.17 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | Providing Functional Household tap connection(Unmetered)125 Nos. in CHAKIARCHHARA Piped Water Supply Scheme under Cooch Behar Division, P.H.E Dte. under Jaldhara Programme |  |  | VCH/000153/2021-2022 |  | 28/05/2021 | 28/05/2021 | CHAKRABORTY ENTERPRISE. | 5.01 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | fhtc |  |  | VCH/001004/2021-2022 | BP-2021-22-273 | 30/10/2021 | 30/10/2021 | KHOKAN DAS | 17.06 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | fhtc matikata |  |  | VCH/000544/2021-2022 | BP-2021-22-111 | 28/07/2021 | 28/07/2021 | ANIMESH DHAR CHOUDHURY | 10.75 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | Providing FHTC & allied work related to pipe line in the command area at Matikata PWSS under Cooch Behar Division, PHED |  |  | VCH/000775/2021-2022 |  | 01/10/2021 | 01/10/2021 | GHOSH AND SAHA CONSTRUCTION | 66.24 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | Providing house connection of drinking water to the house hold of command area under Matikata PWSS under Cooch Behar Division, PHED PART-A |  |  | VCH/000121/2021-2022 |  | 20/04/2021 | 20/04/2021 | ANIMESH DHAR CHOUDHURY | 10.75 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | FHTC PANI SALA |  |  | VCH/000521/2021-2022 | BP-2021-22-50 | 27/07/2021 | 27/07/2021 | CHAKRABORTY ENTERPRISE. | 10.38 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | cost of meterial |  |  | VCH/001169/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 11.14 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | cost of metarial |  |  | VCH/001175/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 5.7 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Matikata Piped Water Suply Scheme | SM/07159 | Retrofitting | cost of meterial |  |  | VCH/001167/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.03 | 0 | 0 | 0
Total | [13 empty] | 210.47 | 0 | 0