## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | Providing house connection of drinking water to the house hold of command area under Khapaidanga PWSS under Cooch Behar Division, P.H.E.D, Part-D |  |  | VCH/001090/2020-2021 |  | 22/03/2021 | 22/03/2021 | BIJOY ROY | 12.25 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | Providing FHTC & other allied work related to pipeline in hte command area at Khapaidanga PWSS under Cooch behar Division,PHED (Part-B) |  |  | VCH/000804/2021-2022 |  | 08/10/2021 | 08/10/2021 | BIJOY ROY | 24.54 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | FHTC AT Khapaidanga Piped Water Suply Scheme |  |  | VCH/000996/2021-2022 | BP-2021-22-278 | 30/10/2021 | 30/10/2021 | BIJOY ROY | 5.04 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | Providing House tap connection of drinking water to the household of command area under Upen Chowki Kuchlibari Water Supply Scheme under Mathabhanga Sub Division, P.H.E. Dte. |  |  | VCH/000866/2021-2022 | 287 | 20/11/2021 | 20/11/2021 | M/S. NITYAGOPAL BANIK | 5.06 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | Providing house connection of drinking water to the household of commend area under Khapaidanga W/S Scheme ( Part-C) of Cooch Behar Division, P.H.E. Dte. Jaldhara Programme. |  |  | VCH/000713/2020-2021 |  | 28/01/2021 | 28/01/2021 | BIJOY ROY | 4.9 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | PROVIDING FHTC NALANGIBARI PWSS |  |  | VCH/000867/2021-2022 |  | 28/10/2021 | 28/10/2021 | DAS ENTERPRISE | 10.12 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | PROVIDING HOUSE CONNECTION OF DRINKING WATER TO THE HOUSEHOLD OF COMMAND AREA UNDER KHAPAIDANGA W.S.S. ( PART - B) OF COB DIVN PHED UNDER JALDHARA PROG. |  |  | VCH/000664/2020-2021 |  | 14/01/2021 | 14/01/2021 | BIJOY ROY | 4.84 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | FHTC AT KALAPANI |  |  | VCH/000930/2021-2022 | BP-2021-22-196 | 11/10/2021 | 11/10/2021 | TAPAN CHANDA | 20.29 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | fhtc |  |  | VCH/001211/2021-2022 | BP-2021-22-328 | 10/12/2021 | 10/12/2021 | SANKAR CHAKRABORTY | 4.13 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | cost of meterial |  |  | VCH/001150/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.32 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | fhtc |  |  | VCH/001124/2021-2022 | BP-2021-22-322 | 09/12/2021 | 09/12/2021 | SWAPAN KUMAR ROY | 9.45 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | FHTC BARA GADAI KHORA |  |  | VCH/000503/2021-2022 | BP-2021_22_47 | 27/07/2021 | 27/07/2021 | BIJOY ROY | 5 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | cost metaral |  |  | VCH/001182/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 2.37 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | supply of chemical |  |  | VCH/001210/2021-2022 | BP-2021-22-317 | 06/12/2021 | 06/12/2021 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 10.88 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | Providing functional household tap connection 120 nos in Baro Pinjarerjhar PWSS under Mathabhanga Sub Division, PHE Dte. under jaldhara Programme. |  |  | VCH/000900/2021-2022 | 310 | 20/11/2021 | 20/11/2021 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 4.71 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | cost metarial |  |  | VCH/001212/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 24.64 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum Rejuvenation of Khapaidanga Piped Water Suply Scheme | SM/07161 | Retrofitting | Providing house connection of drinking water to the household of command area under Khapaidanga PWSS under Cob Divn. PHED,(Part-A) |  |  | VCH/000663/2020-2021 |  | 14/01/2021 | 14/01/2021 | BIJOY ROY | 11.11 | 0 | 0 | 0
Total | [13 empty] | 159.65 | 0 | 0