## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | Providing FHTC & other allied work related to pipeline in the command area at Deocharai PWSS under Cooch behar Division, PHED(Part-A) |  |  | VCH/000119/2021-2022 | null | 20/04/2021 |  | M/S. NITYAGOPAL BANIK | 8.31 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | Providing Functional Household tap connection(Unmetered)125 Nos. in Rajpur Piped Water Supply Scheme under Cooch Behar Division, P.H.E Dte. under Jaldhara Programme |  |  | VCH/000124/2021-2022 | null | 20/04/2021 |  | MATARA CONSTRUCTION CO. | 5.02 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | PROVIDING FHTC UNDER DEOCHOORAI PWSS PART-D |  |  | VCH/000766/2021-2022 | null | 30/09/2021 |  | SANJAY MANDAL | 5.05 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | PROVIDING FHTC AT DEOCHORAI PWSS ( PART-A) |  |  | VCH/000758/2021-2022 | null | 30/09/2021 |  | M/S. NITYAGOPAL BANIK | 14.78 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | fhtc deocharai |  |  | VCH/000545/2021-2022 | BP-2021-22-69 | 27/07/2021 |  | M/S. NITYAGOPAL BANIK | 8.31 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | fhtc |  |  | VCH/000693/2021-2022 | BP-2021_22_155 | 20/08/2021 |  | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 2.46 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | FHTC AT Deocharai |  |  | VCH/000955/2021-2022 | BP-2021-22-236 | 28/10/2021 |  | DIGENDRA CH DEY & SONS | 10.14 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | FHTC AT DEOCHARAI |  |  | VCH/001329/2020-2021 | BP-2021-22-220 | 11/10/2021 |  | MS SURAJIT MAJUMDER | 5.06 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | fhtc |  |  | VCH/001017/2021-2022 | BP-2021-22-202 | 11/10/2021 |  | SWAPAN KR.SARKAR | 0.85 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | Providing household tap connection of drinking water to the household of command area under Paran Majumder Water Supply Scheme under Mathabhanga Sub Division, P.H.E. Dte. under Jalswapna Prakalpa |  |  | VCH/001088/2021-2022 | BP-2021-22-305 | 20/11/2021 |  | M/S. NITYAGOPAL BANIK | 1.52 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | Providing F.H.T.C. & other allied work related to pipe line in the command area at DEOCHARAI PWSS under Cooch Behar Division, PHE Dte. (Part-F) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000192/2021-2022 | 204/TFG | 07/10/2021 | 06/11/2021 | SANJAY MANDAL | 4.76 | 4.53 | 95.06 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | cost of meterial |  |  | VCH/001163/2021-2022 | BP-2021-22-318 | 06/12/2021 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 2.25 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | cost of meterial |  |  | VCH/001157/2021-2022 | BP-2021-22-318 | 06/12/2021 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 2.56 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | fhtc |  |  | VCH/001356/2021-2022 | BP-2021-22-376 | 17/02/2022 |  | NABIN DEBNATH | 15.37 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | fhtc |  |  | VCH/001379/2021-2022 | BP-2021-22-404 | 24/02/2022 |  | ASHIM KUMAR CHAKRABORTY | 4.08 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | fhtc |  |  | VCH/001589/2021-2022 | BP-2021_22_409 | 02/03/2022 |  | NABIN DEBNATH | 5.07 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | fhtc |  |  | VCH/001611/2021-2022 | BP_2021_22_435 | 10/03/2022 |  | ASHIM KUMAR CHAKRABORTY | 11.98 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | FHTC SALMARA |  |  | VCH/001761/2021-2022 | BP-2021_22_454 | 16/03/2022 |  | TAPAN CHANDA | 3.45 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at DEOCHARAI W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000542/2021-2022 | 1642/CD | 29/03/2022 | 28/05/2022 | M/S. NITYAGOPAL BANIK | 41.3 | 0 | 0 | 1
20 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Deocharai Piped Water Suply Scheme to provide FHTC connection to the people of the command area of Deocharai Piped Water Supply Scheme | SM/07162 | Retrofitting | FHTC AT DEOCHARAI |  |  | VCH/000734/2022-2023 | 223 | 02/09/2022 |  | M/S. NITYAGOPAL BANIK | 16.74 | 0 | 0 | 0
Total | [13 empty] | 169.09 | 4.53 | 2.68