## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07163 | Retrofitting | fhtc |  |  | VCH/001135/2021-2022 | BP-2021-22-319 | 09/12/2021 | 09/12/2021 | MS BIDYUT SARKAR | 0.43 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07163 | Retrofitting | PROVIDINH FHTC AT KRISHNAPUR PWSS |  |  | VCH/000715/2021-2022 |  | 14/09/2021 | 14/09/2021 | MS SSB CONSTRUCTION CO | 77.4 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07163 | Retrofitting | PROVIDING FHTC BARO GODAIKHORA PWSS |  |  | VCH/000710/2021-2022 |  | 14/09/2021 | 14/09/2021 | BIJOY ROY | 5.06 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07163 | Retrofitting | FHTC AT KRISHNAPUR |  |  | VCH/000924/2021-2022 | BP-2021-22-190 | 11/10/2021 | 11/10/2021 | SWAPAN KUMAR ROY | 8.92 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07163 | Retrofitting | cost of metarial |  |  | VCH/001179/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.29 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07163 | Retrofitting | Providing house connection of drinking water to the household of command area under Krishnapur W/S Scheme(Part-A) of Cooch Behar Division, PHE Dte. under Jaldhara Programme. |  |  | VCH/000919/2020-2021 |  | 18/03/2021 | 18/03/2021 | NARAYAN CHANDRA BANIK | 7.82 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07163 | Retrofitting | FHTC |  |  | VCH/000971/2021-2022 | BP-2021-22-250 | 28/10/2021 | 28/10/2021 | KAJAL KUMAR DE | 35.33 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07163 | Retrofitting | FHTC AT KRISHNAPUR |  |  | VCH/000933/2021-2022 | BP-2021-22-199 | 11/10/2021 | 11/10/2021 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 5.03 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07163 | Retrofitting | FHTC AT KRISHNAPUR |  |  | VCH/000923/2021-2022 | BP-2021-22-189 | 11/10/2021 | 11/10/2021 | TAPAN CHANDA | 32.45 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Krishnapur Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07163 | Retrofitting | Providing FHTC & other allied works related to pipe line at KRISHNAPUR PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000372/2021-2022 | 1275/CD | 09/02/2022 | 11/03/2022 | BISWAJIT GUHA | 6 | 0 | 0 | 1
Total | [13 empty] | 178.72 | 0 | 0