## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | FHTC CHIKLI |  |  | VCH/000669/2021-2022 | BP-2021-22-71 | 27/07/2021 | 27/07/2021 | GOUTAM KUMAR DAS | 8.21 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Providing house connection of drinking water to the house hold of command area under CHIKLIGURI DWITIA KHANDA PWSS under COB Division, PHED Dte under Jaldhara Programme |  |  | VCH/000103/2021-2022 |  | 06/04/2021 | 06/04/2021 | GOUTAM KUMAR DAS | 8.21 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Providing functional household tap connection(unmetered) 120 nos in Nalangibari Piped W/S Scheme under MTB Sub Division, PHE Dte,. |  |  | VCH/000860/2021-2022 | 290 | 20/11/2021 | 20/11/2021 | PARITOSH PANDIT | 5.06 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Providing FHTC existing connection in the command area at Mara nadirkuthi W.S.S under Cooch Behar Sadar Sub Division, P.H.E. Dte. (Part-C) |  |  | VCH/000809/2021-2022 | 281 | 16/11/2021 | 16/11/2021 | KISHORE BOSE | 5.02 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Providing functional household tap connection(unmetered) 120 nos in Kuchlibari Zone-I Piped W/S Scheme under MTB Sub Division, PHE Dte,. |  |  | VCH/000861/2021-2022 | 300 | 20/11/2021 | 20/11/2021 | RAJIB CHAKRABORTY | 5.06 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Providing functional House hold tap connection(Unmetered)125 Nos in Lauchapra Piped water Supply Scheme under Cooch Behar Division, P.H.E. Dte. under Jaldhara Programme. |  |  | VCH/000159/2021-2022 |  | 28/05/2021 | 28/05/2021 | SOUMITRA BANERJEE | 5.01 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | fhtc lauchapta |  |  | VCH/000565/2021-2022 | BP-2021-22-76 | 28/07/2021 | 28/07/2021 | SOUMITRA BANERJEE | 5.01 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Providng house connection for Chhatoa PWSS under COB P.H.E. Dte. |  |  | VCH/000890/2021-2022 | 307 | 20/11/2021 | 20/11/2021 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 8.11 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | fhtc chkliguri |  |  | VCH/000905/2021-2022 | BP-2021-22-169 | 04/10/2021 | 04/10/2021 | SANKAR BANIK | 1.52 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Providing household tap connection of drinking water to the household of command area under Paran Majumder Water Supply Scheme under Mathabhanga Sub Division, P.H.E. Dte. under Jalswapna Prakalpa |  |  | VCH/001087/2021-2022 | BP-2021-22-305 | 20/11/2021 | 20/11/2021 | M/S. NITYAGOPAL BANIK | 3.53 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Construction of RCC pillar with GI pipe and other allied work for culvert crossing at CHIKLIGURI PWSS under Tufanganj Sub-Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000268/2021-2022 | 201/TFG | 07/10/2021 | 06/11/2021 | GOUTAM KUMAR DAS | 2.46 | 2.44 | 99.17 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Providing FHTC & other allied works at CHIKLIGURI DWITIA KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000250/2022-2023 | 735/CD | 27/08/2022 | 26/09/2022 | GOUTAM KUMAR DAS | 5.54 | 5.53 | 99.84 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Providing household tap connection of drinking water to the household of command area under Paran Majumder Water Supply Scheme under Mathabhanga Sub Division, P.H.E. Dte. under Jalswapna Prakalpa |  |  | VCH/000892/2021-2022 |  | 03/11/2021 | 03/11/2021 | M/S. NITYAGOPAL BANIK | 5.05 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | FHTC |  |  | VCH/001642/2021-2022 | BP-2021_22_468 | 17/03/2022 | 17/03/2022 | KAJAL KUMAR DE | 20.62 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | FHTC |  |  | VCH/001770/2021-2022 | BP-2021_22_454 | 16/03/2022 | 16/03/2022 | TAPAN CHANDA | 0.42 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | FHTC |  |  | VCH/001771/2021-2022 | BP-2021_22_462 | 16/03/2022 | 16/03/2022 | MS DD ENTERPRISE | 3.05 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Providing House Connection of drinking water to the house hold of command Area under CHIKLIGURI DWITIYA KHANDA PWSS under Cooch Behar Division, PHED PART - A | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000059/2020-2021 | 1112/CD | 16/10/2020 | 14/01/2021 | GOUTAM KUMAR DAS | 8.11 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Chikliguri Dwitia Khanda Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07164 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000061/2021-2022 | 1201/CD | 01/02/2022 | 01/02/2022 | Resource Division | 0.55 | 0 | 0 | 0
Total | [13 empty] | 100.52 | 7.96 | 7.92