## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | Construction of pathway and inside drain in the second site of BILSI WSS under Tufanganj Sub-Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000239/2021-2022 | 118/TFG | 23/08/2021 | 22/09/2021 | NABIN DEBNATH | 2.31 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | Providing F.H.T.C & other allied work related to Pipe Line in the Command area at BILSI PWSS under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000166/2020-2021 | 1438/CD | 08/01/2021 | 08/04/2021 | NABIN DEBNATH | 62.45 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | PP KIT TEST |  |  | VCH/001228/2021-2022 | BP-2021-22-336 | 13/01/2022 | 13/01/2022 | GREEN ECONOMY INISTIVES PVT LTD | 0.04 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | FHTC BILSI |  |  | VCH/001225/2021-2022 | BP-2021-22-351 | 25/01/2022 | 25/01/2022 | PARITOSH PANDIT | 5.07 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | fhtc |  |  | VCH/001360/2021-2022 | BP-2021-22-381 | 11/02/2022 | 11/02/2022 | TAPU BANIK | 10.12 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | FHTC |  |  | VCH/001218/2021-2022 | BP-2021-22-348 | 25/01/2022 | 25/01/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.9 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | fhtc |  |  | VCH/001374/2021-2022 | BP-2021-22-394 | 22/02/2022 | 22/02/2022 | SANKAR CHAKRABORTY | 0.87 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | COST OF PIPES |  |  | VCH/001757/2021-2022 | BP-2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.02 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | FHTC |  |  | VCH/001216/2021-2022 | BP-2021-22-341 | 27/01/2022 | 27/01/2022 | NABIN DEBNATH | 2.3 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | fhtc |  |  | VCH/001361/2021-2022 | BP-2021-22-386 | 17/02/2022 | 17/02/2022 | UTPAL CHAKRABORTY | 5.05 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | FHTC |  |  | VCH/001226/2021-2022 | BP-2021-22-346 | 21/01/2022 | 21/01/2022 | MATARA CONSTRUCTION CO. | 11 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | FHTC |  |  | VCH/001223/2021-2022 | BP-2021-22-343 | 27/01/2022 | 27/01/2022 | PINAKI SAHA | 0.04 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | FHTC |  |  | VCH/001222/2021-2022 | BP-2021-22-352 | 25/01/2022 | 25/01/2022 | MS BIDYUT SARKAR | 4.37 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | FHTC |  |  | VCH/001224/2021-2022 | BP-2021-22-354 | 25/01/2022 | 25/01/2022 | SANKAR CHAKRABORTY | 0.13 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | COST OF PIPES |  |  | VCH/001747/2021-2022 | BP-2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 30.21 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | FHTC |  |  | VCH/001217/2021-2022 | BP-2021-22-345 | 20/01/2022 | 20/01/2022 | TAPU BANIK | 0.35 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | FHTC |  |  | VCH/001227/2021-2022 | BP-2021-22-347 | 25/01/2022 | 25/01/2022 | TAPAN CHANDA | 12.45 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | fhtc |  |  | VCH/001592/2021-2022 | BP-2021_22_413 | 02/03/2022 | 02/03/2022 | SAMBHU BANIK | 0.64 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 790/CD | 07/12/2021 | 07/12/2021 | Resource Division | 61.49 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 68/CD | 12/04/2022 | 12/04/2022 | Resource Division | 2.75 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bilsi Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07165 | Retrofitting | HIRING VEHICLE |  |  | BILL/00489/2024-2025 | BP-224 | 01/08/2024 | 01/08/2024 | ANIMESH DHAR CHOUDHURY | 0.36 | 0 | 0 | 0
Total | [13 empty] | 216.89 | 0 | 0