## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | Providing functional household tap connection under SIKARPUR Piped water Supply Scheme under Cooch Behar Division, P.H.E. Dte. under jaldhara Programme( Phase-II) |  |  | VCH/000114/2021-2022 |  | 20/04/2021 | 20/04/2021 | ASHIT KUMAR GHOSH | 5.02 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | FHTC GOSKADANGA |  |  | VCH/000612/2021-2022 | BP-2021-22-143 | 17/08/2021 | 17/08/2021 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.85 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | Providing house connection & drinking water to the household of command area under Bhandijalas (Part-B) of Tufanganj Sub Division under Jaldhara Prpogramme. |  |  | VCH/000926/2020-2021 |  | 18/03/2021 | 18/03/2021 | GOUTAM KUMAR DAS | 5.05 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | PROFIDING FHTC AT BHANDIJALAS PWSS |  |  | VCH/000757/2021-2022 |  | 30/09/2021 | 30/09/2021 | GOUTAM KUMAR DAS | 6.11 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | Providing functional house hold connection(unmetered) 125 Nos in Ghoksadanga Piped water supply scheme under Mathabhanga Sub Division, P.H.E. Dte. under Jaldhara Programme. |  |  | VCH/000156/2021-2022 |  | 28/05/2021 | 28/05/2021 | MODERN UN EMPLOYED LABOUR CO-OPEARATIVE. | 4.85 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | PROVIDING FHTC UNDER BHANDIJALAS PWSS |  |  | VCH/000778/2021-2022 |  | 01/10/2021 | 01/10/2021 | GOUTAM KUMAR DAS | 5.07 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | cost metaral |  |  | VCH/001185/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.51 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | Providing FHTC & other allied work related to pipeline in the command area at Bhandijalas PWSS under Cooch behar Division, PHED(Part-A) |  |  | VCH/000118/2021-2022 |  | 20/04/2021 | 20/04/2021 | KAJAL KR. DEY | 16.78 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | prov. fhtc at bhandijalus |  |  | VCH/000237/2021-2022 | 11 | 12/05/2021 | 12/05/2021 | GOUTAM KUMAR DAS | 5.05 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | FHTC AT Bhandijalas |  |  | VCH/000990/2021-2022 | BP-2021-22-270 | 30/10/2021 | 30/10/2021 | UTPAL CHAKRABORTY | 25.67 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | fhtc |  |  | VCH/001019/2021-2022 | BP-2021-22-166 | 04/10/2021 | 04/10/2021 | SWAPAN KUMAR ROY | 11.26 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | fhtc |  |  | VCH/000906/2021-2022 | BP-2021-22-170 | 04/10/2021 | 04/10/2021 | PALLAB BHAWAL | 4.97 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | FHTC AT Bhandijalas |  |  | VCH/001326/2020-2021 | BP-2021-22-217 | 11/10/2021 | 11/10/2021 | PINAKI SAHA | 4.98 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | fhtc bhandijilash |  |  | VCH/000560/2021-2022 | BP-2021-22-87 | 27/07/2021 | 27/07/2021 | KAJAL KUMAR DE | 16.78 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | PROVIDING FHTC AT DEOCHORAI PWSS ( PART-A) |  |  | VCH/000512/2021-2022 |  | 07/09/2021 | 07/09/2021 | M/S. NITYAGOPAL BANIK | 40.96 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | cost of meterial |  |  | VCH/001173/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 13.81 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | cost of meterial |  |  | VCH/001158/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.04 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at BHANDIJALAS W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000529/2021-2022 | 1629/CD | 29/03/2022 | 28/05/2022 | GOUTAM KUMAR DAS | 49.5 | 2.79 | 5.64 | 100
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000055/2021-2022 | 1197/CD | 01/02/2022 | 01/02/2022 | Resource Division | 1.1 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 66/CD | 12/04/2022 | 12/04/2022 | Resource Division | 3.3 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Retrofitting of existing Bhandijalas Piped Water Suply Scheme to provide FHTC connection to the people of the command area of the Scheme | SM/07167 | Retrofitting | FHTC AT BHANDIJALAS PWSS |  |  | BILL/00653/2022-2023 | BP-461-22-23-P | 01/12/2022 | 01/12/2022 | GOUTAM KUMAR DAS | 0.9 | 0 | 0 | 0
Total | [13 empty] | 226.55 | 2.79 | 1.23