## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | Providing house connection for Takoamari PWSS under COB PHE |  |  | VCH/000887/2021-2022 | 311 | 20/11/2021 | 20/11/2021 | ORIENTAL CO OP LABOUR CONTRACT CONSTRUCTION SO | 12.17 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | PROVIDING FHTC IN RAMTHENGA PWSS |  |  | VCH/000896/2021-2022 |  | 03/11/2021 | 03/11/2021 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.9 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | Providing functional household tap connection ( unmetered)120 Nos in Sikarpur piped W/S Scheme under Mathabhanga Sub Division, PHE Dte. |  |  | VCH/000898/2021-2022 | 308 | 20/11/2021 | 20/11/2021 | ASHIT KUMAR GHOSH | 5.06 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | PROVIDING FHTC ( 125NOS) IN BARO KAIMARI PWSSUNDER MTB |  |  | VCH/000897/2021-2022 | 299 | 20/11/2021 | 20/11/2021 | SUBODH ROY & SONS | 5 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | Providing 140 nos. F.H.T.C. Connection in the command area at Putimari P.W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000316/2021-2022 | 455/SD | 29/12/2021 | 13/01/2022 | SIDHARTHA ROY | 4.94 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | fhtc |  |  | VCH/001384/2021-2022 | BP-2021-22-399 | 22/02/2022 | 22/02/2022 | SANKAR BANIK | 20.87 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | FHTC |  |  | VCH/001644/2021-2022 | BP-2021_22_466 | 17/03/2022 | 17/03/2022 | PARITOSH PANDIT | 5.01 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | COST PIPES |  |  | VCH/001751/2021-2022 | BP-2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 7.91 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | FHTC |  |  | VCH/001765/2021-2022 | BP-2021_22_454 | 16/03/2022 | 16/03/2022 | TAPAN CHANDA | 1.03 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | fhtc |  |  | VCH/001133/2021-2022 | BP-2021-22-319 | 09/12/2021 | 09/12/2021 | MS BIDYUT SARKAR | 4.9 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | fhtc |  |  | VCH/001353/2021-2022 | BP-2021-22-373 | 11/02/2022 | 11/02/2022 | RAJIB CHAKRABORTY | 9.99 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | FHTC |  |  | VCH/001689/2021-2022 | BP_2021_22_504 | 31/03/2022 | 31/03/2022 | SWAPAN KUMAR ROY | 4.93 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | FHTC |  |  | VCH/001656/2021-2022 | BP_2021_22_475 | 25/03/2022 | 25/03/2022 | SWAPAN KR.SARKAR | 14.11 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | PROCUREMENT CHEMICAL GLASSWARE FOR MKHLIGANJ LABORATORY |  |  | BILL/00571/2023-2024 | BP-92 | 04/05/2023 | 04/05/2023 | DULAL MAJUMDER | 3.13 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Water Supply Schem | SM/08145 | Retrofitting | PROVIDING INTERNET CONNECTION |  |  | BILL/00600/2024-2025 | BP-235 | 01/08/2024 | 01/08/2024 | BIJOY ROY | 0.1 | 0 | 0 | 0
Total | [13 empty] | 104.05 | 0 | 0