## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bhanga More Water Supply Scheme | SM/08148 | Retrofitting | Laying of Pipe Line & other allied work related to F.H.T.C. under JJM Programme for BHANGAMORE PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000016/2021-2022 | 140/CD | 06/07/2021 | 04/10/2021 | NANDALAL SARKAR | 37.34 | 23.75 | 63.6 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bhanga More Water Supply Scheme | SM/08148 | Retrofitting | PROVIDING FHTC UNDER BHANGA MORE PWSS |  |  | VCH/000725/2021-2022 |  | 22/09/2021 | 22/09/2021 | NABIN DEBNATH | 5.08 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bhanga More Water Supply Scheme | SM/08148 | Retrofitting | Providing FHTC and Laying of Pipe line at BHANGAMORE PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000407/2021-2022 | 1465/CD | 10/03/2022 | 09/04/2022 | NABIN DEBNATH | 45.25 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bhanga More Water Supply Scheme | SM/08148 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 65/CD | 12/04/2022 | 12/04/2022 | Resource Division | 3.58 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bhanga More Water Supply Scheme | SM/08148 | Retrofitting | PAYMENT TO RESOURCE DIV |  |  | VCH/001338/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 46.86 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bhanga More Water Supply Scheme | SM/08148 | Retrofitting | FHTC |  |  | VCH/001766/2021-2022 | BP-2021_22_454 | 16/03/2022 | 16/03/2022 | TAPAN CHANDA | 2.83 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Bhanga More Water Supply Scheme | SM/08148 | Retrofitting | fhtc |  |  | VCH/001365/2021-2022 | BP-2021-22-384 | 17/02/2022 | 17/02/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 0.29 | 0 | 0 | 0
Total | [13 empty] | 141.23 | 23.75 | 16.81