## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhat khater Bari Water Supply Scheme | SM/08149 | Retrofitting | Providing house connection of drinking water to the household of command area under Chatkhaterbari PWSS Under Mathabhanga Sub Division, PHE Dte. under Jaldhara Pragramme. |  |  | VCH/000123/2021-2022 |  | 20/04/2021 | 20/04/2021 | PINAKI SAHA | 5.01 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhat khater Bari Water Supply Scheme | SM/08149 | Retrofitting | Providing functional house hold tap connection (unmetered) 135 nos. in CHHAT KHATERBARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000324/2021-2022 | 324/MTB | 04/01/2022 | 19/01/2022 | PINAKI SAHA | 5.01 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhat khater Bari Water Supply Scheme | SM/08149 | Retrofitting | FHTC |  |  | VCH/001662/2021-2022 | BP_2021_22_481 | 30/03/2022 | 30/03/2022 | SANKAR CHAKRABORTY | 14.03 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhat khater Bari Water Supply Scheme | SM/08149 | Retrofitting | COST OF PIOES |  |  | VCH/001752/2021-2022 | BP-2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 5.97 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhat khater Bari Water Supply Scheme | SM/08149 | Retrofitting | PAYMENT TO RESOUCE DIV |  |  | VCH/001337/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 20 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhat khater Bari Water Supply Scheme | SM/08149 | Retrofitting | FHTC AT CHHAT KATHERBARI PWSS |  |  | VCH/000886/2022-2023 | 326 | 30/09/2022 | 30/09/2022 | PINAKI SAHA | 13.57 | 0 | 0 | 0
Total | [13 empty] | 63.59 | 0 | 0