## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | Providing FHTC 125 nos for Ramthenga PWSS |  |  | VCH/000907/2020-2021 | null | 18/03/2021 |  | MODERN UN EMPLOYED LABOUR CO-OPEARATIVE. | 4.86 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | fhtc ramthenga pwss |  |  | VCH/000230/2021-2022 | 11 | 12/05/2021 |  | MODERN UN EMPLOYED LABOUR CO-OPEARATIVE. | 4.86 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | Providing House hold tap connection of drinking water to the house hold of command area under Nagar Changrabandha W/S Scheme under Mathabhanga Sub Division |  |  | VCH/000699/2021-2022 | null | 13/09/2021 |  | RELIANCE UN EMPLOYED ENGINEERS CO OP SOC LTD | 5.06 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | PROVIDING FHTC UNDER RAMTHENGA PWSS |  |  | VCH/000769/2021-2022 | null | 30/09/2021 |  | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 5.03 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | PROVIDING FHTC UNDER CHAKIAR CHHARA PWSS |  |  | VCH/000767/2021-2022 | null | 30/09/2021 |  | PINAKI SAHA | 4.98 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | fhtc |  |  | VCH/000969/2021-2022 | BP-2021-22-248 | 28/10/2021 |  | DIGENDRA CH DEY & SONS | 5.01 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | FHTC AT RAMTHANGA |  |  | VCH/000944/2021-2022 | BP-2021-22-211 | 11/10/2021 |  | NABIN DEBNATH | 5.08 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | FHTC AT RAMTHANGA |  |  | VCH/000992/2021-2022 | BP-2021-22-272 | 30/10/2021 |  | NANDALAL SARKAR | 4.97 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | Providing functional household tap connection ( unmetered)120 Nos in RAMTHENGA piped W/S Scheme under Mathabhanga Sub Division, PHE Dte. under Jaldhara Programme |  |  | VCH/000862/2021-2022 | 286 | 16/11/2021 |  | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 5.14 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | cost meterial |  |  | VCH/001144/2021-2022 | BP-2021-22-318 | 06/12/2021 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.01 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | water testing report |  |  | VCH/001140/2021-2022 | BP-2021-22-330 | 13/12/2021 |  | GREEN ECONOMY INISTIVES PVT LTD | 0.02 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | Providing functional house hold tap connection (unmetered) 135 nos. in RAMTHANGA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000311/2021-2022 | 331/MTB | 04/01/2022 | 19/01/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 5.01 | 0 | 0 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | fhtc |  |  | VCH/001348/2021-2022 | BP-2021-22-368 | 17/02/2022 |  | NABIN DEBNATH | 24.38 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | fhtc |  |  | VCH/001352/2021-2022 | BP-2021-22-372 | 17/02/2022 |  | SWAPAN KUMAR ROY | 2.91 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | Providing functional house hold tap connection (unmetered) 135 nos. in RAMTHANGA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000495/2021-2022 | 461/MTB | 04/03/2022 | 19/03/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.98 | 0 | 0 | 1
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | FHTC |  |  | VCH/001760/2021-2022 | BP-2021_22_414 | 03/03/2022 |  | ASHIM KUMAR CHAKRABORTY | 2.44 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | fhtc charaljani |  |  | VCH/000016/2022-2023 | BP-2022_23_01 | 07/04/2022 |  | SUSHANTA SAHA | 7.3 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | FHTC |  |  | VCH/000086/2022-2023 | BP_22_23_55 | 28/04/2022 |  | SHYAMAL NATH | 2.97 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | FHTC |  |  | VCH/000089/2022-2023 | BP_22_23_55 | 28/04/2022 |  | SHYAMAL NATH | 3.26 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | FHTC |  |  | VCH/000098/2022-2023 | BP-2022-23-22 | 13/04/2022 |  | ASHIM KUMAR CHAKRABORTY | 0.14 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | Providing functional house hold tap connection within command area under RAMTHANGA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000114/2022-2023 | 121/MTB | 23/06/2022 | 08/07/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.81 | 4.81 | 100 | 1
22 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | UPLOADING |  |  | VCH/000404/2022-2023 | BP-22-23-140 | 14/07/2022 |  | DEBNATH ENTERPRISE | 1.64 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | Providing FHTC and Laying of Pipe line at RAMTHENGA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000414/2021-2022 | 1472/CD | 10/03/2022 | 09/04/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 31.89 | 0 | 0 | 1
24 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Ramthanga Water Supply Scheme | SM/08151 | Retrofitting | Laying of Pipe Line & other allied work related to F.H.T.C. under JJM Programme for RAMTHENGA PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000013/2021-2022 | 137/CD | 06/07/2021 | 04/10/2021 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 15.13 | 14.44 | 95.41 | 0
Total | [13 empty] | 151.86 | 19.24 | 12.67