## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Laying of Pipe Line & other allied work related to F.H.T.C. under JJM Programme for UTTAR FULKARDABRI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000018/2021-2022 | 142/CD | 06/07/2021 | 04/10/2021 | SHIBA ENTERPRISE | 35.34 | 30.31 | 85.78 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Providing house connection of drinking water to the house hold of command area under Uttar Fulkardabri PWSS under Cooch Behar Division, PHED Dte under Jaldhara Programme |  |  | VCH/001088/2020-2021 |  | 22/03/2021 | 22/03/2021 | MANABENDRA DE | 5.01 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Providing house connection of drinking water to the house hold of command area under uttar Fulkardabri PWSS under Cooch Behar Division, PHED Dte under Jaldhara Programme |  |  | VCH/000347/2021-2022 |  | 16/07/2021 | 16/07/2021 | TISTA LABOUR CO-OP CONT AND CONST SOCIETY LTD | 5.01 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | cost of meterial |  |  | VCH/001152/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FHTC MARICH BARI |  |  | VCH/000621/2021-2022 | BP-2021-22-150 | 17/08/2021 | 17/08/2021 | ANIMESH DHAR CHOUDHURY | 3.2 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Providing functional house hold tap connection (unmetered) 135 nos. in UTTAR FULKARDABRI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000318/2021-2022 | 333/MTB | 04/01/2022 | 19/01/2022 | RELIANCE UN EMPLOYED ENGINEERS CO OP SOC LTD | 5 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Providing FHTC and Laying of Pipe line at UTTAR FULKADABRI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000405/2021-2022 | 1463/CD | 10/03/2022 | 09/04/2022 | SHIBA ENTERPRISE | 37.85 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000028/2021-2022 | 1105/CD | 27/01/2022 | 27/01/2022 | Resource Division | 29.6 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FHTC |  |  | VCH/001346/2021-2022 | BP-2021-22-400 | 17/02/2022 | 17/02/2022 | M/S. NITYAGOPAL BANIK | 28.17 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | COST PIPES |  |  | VCH/001754/2021-2022 | BP-2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 5.73 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FHTC |  |  | VCH/001608/2021-2022 | BP_2021_22_432 | 10/03/2022 | 10/03/2022 | GOUTAM KUMAR DAS | 5.01 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FHTC |  |  | VCH/000105/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 0.35 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FHTC |  |  | VCH/001623/2021-2022 | BP_2021_22_447 | 11/03/2022 | 11/03/2022 | PINAKI SAHA | 3.22 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | FGHTC |  |  | VCH/001773/2021-2022 | BP-2021_22_462 | 16/03/2022 | 16/03/2022 | TAPAN CHANDA | 0.38 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of UTTAR FULKAR DABRI Water Supply Scheme | SM/08152 | Retrofitting | fhtc |  |  | VCH/001598/2021-2022 | BP-2021-22-421 | 11/03/2022 | 11/03/2022 | MS BIDYUT SARKAR | 12.14 | 0 | 0 | 0
Total | [13 empty] | 176.02 | 30.31 | 17.22