## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | cost of meterial |  |  | VCH/001153/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 3.67 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | Providing FHTC under Kawardara PWSS |  |  | VCH/000904/2020-2021 |  | 18/03/2021 | 18/03/2021 | SEKHAR GHOSAL | 5.01 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | FHTC CHATOYA |  |  | VCH/000574/2021-2022 | BP-2021-22-109 | 28/07/2021 | 28/07/2021 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 5.05 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | PROVIDING FHTC GHUGHUMARI PWSS |  |  | VCH/000524/2021-2022 |  | 08/09/2021 | 08/09/2021 | SARKAR CONSTRUCTION | 10.09 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | PROVIDING FHTC UNDER CHARALJANI PWSS PART - B |  |  | VCH/000728/2021-2022 |  | 24/09/2021 | 24/09/2021 | SUSHANTA SAHA | 9.26 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | PROVIDING FHTC IN KISMAT BHATRGACHHI PWSS ( P-A ) |  |  | VCH/000523/2021-2022 |  | 08/09/2021 | 08/09/2021 | M/S BADAL CH SAHA | 24.23 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | fhtc |  |  | VCH/000934/2021-2022 | BP-2021-22-200 | 11/10/2021 | 11/10/2021 | M/S. MANDAL CONSTRUCTION | 30.75 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | cost of meterial |  |  | VCH/001159/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 1.63 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | CHHATOA |  |  | VCH/000575/2021-2022 | BP-2021-22-109 | 28/07/2021 | 28/07/2021 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 3.09 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | fhtc |  |  | VCH/001015/2021-2022 | BP-2021-22-164 | 04/10/2021 | 04/10/2021 | ASHIM KUMAR CHAKRABORTY | 7.63 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | Providing house connection of drinking water to the household of command area under CHARALJANI W/S Scheme ( Part-B) of Tufanganj Sub Division, P.H.E. Dte. under Jaldhara Programme. |  |  | VCH/000144/2021-2022 |  | 04/05/2021 | 04/05/2021 | SUSHANTA SAHA | 5.05 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | Providing FHTC & other allied works at CHARALJANI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000421/2022-2023 | 1279/CD | 02/12/2022 | 31/01/2023 | SUSHANTA SAHA | 48.71 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | fhtc |  |  | VCH/001357/2021-2022 | BP-2021-22-377 | 17/02/2022 | 17/02/2022 | RAJIB CHAKRABORTY | 5.07 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | FHTC AT CHARALJANI |  |  | VCH/000803/2022-2023 | 305 | 30/09/2022 | 30/09/2022 | SUSHANTA SAHA | 9.33 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | fhtc |  |  | VCH/001358/2021-2022 | BP-2021-22-378 | 17/02/2022 | 17/02/2022 | SIDHARTHA ROY | 3.03 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | FHTC |  |  | VCH/001661/2021-2022 | BP_2021_22_480 | 25/03/2022 | 25/03/2022 | ASHIM KUMAR CHAKRABORTY | 8.77 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of CHARALJANI Water Supply Scheme | SM/08153 | Retrofitting | FGTC |  |  | VCH/000102/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 0.38 | 0 | 0 | 0
Total | [13 empty] | 180.76 | 0 | 0