## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | FHTC AT BOGDABARI KESAIBARI |  |  | VCH/000950/2021-2022 | BP-2021-22-228 | 11/10/2021 | 11/10/2021 | SIBAPADA SINGHA ROY | 4.9 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | fhtc |  |  | VCH/001014/2021-2022 | BP-2021-22-238 | 28/10/2021 | 28/10/2021 | MS SSB CONSTRUCTION CO | 10.64 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | FHTC AT RAMTHANGA |  |  | VCH/000943/2021-2022 | BP-2021-22-210 | 11/10/2021 | 11/10/2021 | BIJOY ROY | 3.64 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | FHTC RAJPUR BHOGDABRI KESRIBARI |  |  | VCH/000499/2021-2022 | BP-2021-22-44 | 27/07/2021 | 27/07/2021 | MATARA CONSTRUCTION CO. | 17.57 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | Providing FHTC & other allied works in the command area of Panisala PWSS under Cooch Behar Division, PHED Part-B |  |  | VCH/000913/2020-2021 |  | 18/03/2021 | 18/03/2021 | SAMBHU BANIK | 24.31 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | fhtc |  |  | VCH/000957/2021-2022 | BP-2021-22-238 | 28/10/2021 | 28/10/2021 | MS SSB CONSTRUCTION CO | 34.36 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | FHTC AT BHOGDABRI KEASRI ABRI |  |  | VCH/000945/2021-2022 | BP-2021-22-212 | 11/10/2021 | 11/10/2021 | GHOSH AND SAHA CONSTRUCTION | 6.91 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | Providing house hold connection of drinking water to the house hold of command area under Bhogdabri Kesaribari PWSS under Cooch Behar Division, PHED Part-c |  |  | VCH/000922/2020-2021 |  | 18/03/2021 | 18/03/2021 | BIPUL SARKAR | 4.75 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | cons oof svchamber ssp drin platform pathway bhogdabri kesribari |  |  | VCH/000258/2021-2022 | 10 | 12/05/2021 | 12/05/2021 | MS BIDYUT SARKAR | 10.51 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | PROVIDING FHTC AT NAKKATIGACHHI PWSS |  |  | VCH/000714/2021-2022 |  | 14/09/2021 | 14/09/2021 | ASHIM KUMAR CHAKRABORTY | 59.48 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | Providing House connection for BHOGDABRI KESIABARI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000329/2021-2022 | 1230/CD | 09/02/2022 | 11/03/2022 | MS BIDYUT SARKAR | 14.04 | 0 | 0 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 1186/CD | 01/02/2022 | 01/02/2022 | Resource Division | 3.74 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of BOGDABARI KESAIBARI Water Supply Scheme | SM/08154 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 60/CD | 12/04/2022 | 12/04/2022 | Resource Division | 3.29 | 0 | 0 | 0
Total | [13 empty] | 198.14 | 0 | 0