## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | Providing Functional Household tap connection(Unmetered)125 Nos. in Tutiarkuthi Piped Water Supply Scheme under Cooch Behar Division, P.H.E Dte. under Jaldhara Programme |  |  | VCH/000115/2021-2022 |  | 20/04/2021 | 20/04/2021 | SOUMITRA BANERJEE | 5.01 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | FHTC UTTAR FULKADABRI |  |  | VCH/000585/2021-2022 | BP-2021-22-104 | 28/07/2021 | 28/07/2021 | TISTA LABOUR CO-OP CONT AND CONST SOCIETY LTD | 5.01 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | FHTC BARA KAI MARI |  |  | VCH/000579/2021-2022 | BP-2021-22-103 | 28/07/2021 | 28/07/2021 | SUBODH ROY & SONS | 5 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | LAYING PIPE LINE RELATED TO FHTC UNDER JJM PROGRAMME FOR KUMIRGHAT PWSS |  |  | VCH/000761/2021-2022 |  | 30/09/2021 | 30/09/2021 | ANIMESH DHAR CHOUDHURY | 12.17 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | CONSTN 250 M CAPACITY RCC OHR WITH 20 MTR STAGING HEIGHT FOR KUMIRGHAT PWSS UNDER COB DivN PHED |  |  | VCH/000187/2021-2022 |  | 28/05/2021 | 28/05/2021 | GHOSH AND SAHA CONSTRUCTION | 45.8 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | FHTC KUMIRGHAT |  |  | VCH/000994/2021-2022 | BP-2021-22-276 | 30/10/2021 | 30/10/2021 | SWAPAN KUMAR ROY | 7.2 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | FHTC SALBARI W/S/S |  |  | VCH/000581/2021-2022 | BP-2021-22-96 | 30/07/2021 | 30/07/2021 | TAPU BANIK | 4.94 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | FHTC AT KUMIRGHAT |  |  | VCH/000940/2021-2022 | BP-2021-22-206 | 11/10/2021 | 11/10/2021 | NORTHE BENGAL CONST CO | 4.94 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | CIDF COONCETION BHANDIJILASH |  |  | VCH/000602/2021-2022 | BP-2021-22-131 | 12/08/2021 | 12/08/2021 | GOUTAM KUMAR DAS | 4.2 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | CONST OF SSP POST ETC AT EKMUKHA |  |  | VCH/000595/2021-2022 | BP-2021-22-125 | 18/08/2021 | 18/08/2021 | MS SSB CONSTRUCTION CO | 2.83 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | FHTC PURBA FULKAR DABRI |  |  | VCH/000584/2021-2022 | BP-2021-22-91 | 28/07/2021 | 28/07/2021 | MANABENDRA DE | 5.03 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | cost of metarial |  |  | VCH/001176/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.48 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | FHTC KORALA WSS |  |  | VCH/000582/2021-2022 | BP-2021-22-89 | 28/07/2021 | 28/07/2021 | GEETA CONSTRUCTION | 5 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | fhtc tutier kuthi |  |  | VCH/000541/2021-2022 | BP-2021-22-62 | 27/07/2021 | 27/07/2021 | SOUMITRA BANERJEE | 5.01 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | FHTC PANISALA |  |  | VCH/000663/2021-2022 | BP-2021-22-53 | 28/07/2021 | 28/07/2021 | GOUTAM KUMAR DAS | 8.11 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | SSP EKMUKHA |  |  | VCH/000688/2021-2022 | BP-2021_22_125 | 12/08/2021 | 12/08/2021 | MS SSB CONSTRUCTION CO | 0.4 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | fhtc lauchapra |  |  | VCH/000569/2021-2022 | BP-2021-22-75 | 28/07/2021 | 28/07/2021 | SAUMITRA BANERJEE | 4.83 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Kumirghat Water Supply Scheme | SM/08155 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000067/2021-2022 | 1362/CD | 24/02/2022 | 24/02/2022 | Resource Division | 26.34 | 0 | 0 | 0
Total | [13 empty] | 152.31 | 0 | 0