## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | Providing FHTC & other allied works in the command area of Panisala PWSS under Cooch Behar Division, PHED Part-D |  |  | VCH/000909/2020-2021 | null | 18/03/2021 |  | ASIM KAR | 5.04 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | CPST OF FUEL AE SADR AND RWS |  |  | VCH/000590/2021-2022 | BP-2021-22-118 | 04/08/2021 |  | R.C.BANIK & SONS | 3.2 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | PROVIDING FHTC DAKHIN BAJEJAMAPWSS |  |  | VCH/000709/2021-2022 | null | 14/09/2021 |  | DAS ENTERPRISE | 5.07 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | fhtc |  |  | VCH/000935/2021-2022 | BP-2021-22-201 | 11/10/2021 |  | PARITOSH PANDIT | 5.06 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | FHTC |  |  | VCH/000976/2021-2022 | BP-2021-22-255 | 30/10/2021 |  | NABIN DEBNATH | 5.05 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | laying of pipeline & other allied work related to FHTC under JJM Programme for Putimari Phuleswari PWSS under Cooch Behar Division, P.H.E. Dte. |  |  | VCH/000884/2021-2022 | BP-2021-22-296 | 14/11/2021 |  | GHOSH AND SAHA CONSTRUCTION | 45.71 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | PROVIDING FHTC ANDARAN NIZTARAF |  |  | VCH/000708/2021-2022 | null | 14/09/2021 |  | DAS ENTERPRISE | 5.04 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | cost of meterial |  |  | VCH/001154/2021-2022 | BP-2021-22-318 | 06/12/2021 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.03 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | fhtc |  |  | VCH/001349/2021-2022 | BP-2021-22-369 | 17/02/2022 |  | NABIN DEBNATH | 5.04 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | fhtc |  |  | VCH/001351/2021-2022 | BP-2021-22-371 | 17/02/2022 |  | SWAPAN KUMAR ROY | 1.86 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | fhtc |  |  | VCH/001366/2021-2022 | BP-2021-22-385 | 17/02/2022 |  | MS BIDYUT SARKAR | 13.56 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | fhtc |  |  | VCH/001382/2021-2022 | BP-2021-22-401 | 24/02/2022 |  | GOUTAM KUMAR DAS | 5.02 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | FHTC |  |  | VCH/001684/2021-2022 | BP_2021_22_499 | 30/03/2022 |  | MALAY KR.DEB | 34.08 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | fhtc |  |  | VCH/001641/2021-2022 | BP-2021_22_465 | 16/03/2022 |  | ALOK ENTERPRISE | 4.08 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | FHTC |  |  | VCH/000099/2022-2023 | BP-2022-23-22 | 13/04/2022 |  | ASHIM KUMAR CHAKRABORTY | 0.33 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | Providing F.H.T.C & Restoration of damage Pipeline allied Work at GOPALPUR Water Supply Scheme P.H.E Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000317/2022-2023 | 926/CD | 26/09/2022 | 26/10/2022 | SANKAR BANIK | 4.33 | 0 | 0 | 1
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | Providing House connection for GOPALPUR PWSS under Cooch Behar Division. PHE Dte PART Z | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000057/2022-2023 | 254/CD | 24/05/2022 | 23/06/2022 | SANKAR BANIK | 8.04 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Gopalpur Water Supply Scheme | SM/08156 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000044/2021-2022 | 1195/CD | 01/02/2022 |  | Resource Division | 1.37 | 0 | 0 | 0
Total | [13 empty] | 151.9 | 0 | 0