## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | FHTC at Chagalber |  |  | VCH/000242/2021-2022 | 11 | 12/05/2021 | 12/05/2021 | GEETA CONSTRUCTION | 4.98 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | Providing functional House hold tap connection(Unmetered)125 Nos in Chagalber Piped water Supply Scheme under Cooch Behar Division, P.H.E. Dte. under Jaldhara Programme. |  |  | VCH/000916/2020-2021 |  | 18/03/2021 | 18/03/2021 | GEETA CONSTRUCTION | 4.98 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | Laying of Pipe Line & other allied work related to F.H.T.C. under JJM Programme for CHHAGALBER PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000006/2021-2022 | 130/CD | 06/07/2021 | 04/10/2021 | GEETA CONSTRUCTION | 49.38 | 43.77 | 88.64 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at CHHAGALBER W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000535/2021-2022 | 1635/CD | 29/03/2022 | 28/05/2022 | NARAYAN CHANDRA BANIK | 39 | 23.81 | 61.06 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of CHHAGALBER PWSS under Cooch Behar Division PHE Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000501/2021-2022 | 1449/CD | 10/03/2022 | 09/04/2022 | AUXILIARY TUBEWELL DRILLERS | 10.7 | 9.48 | 88.6 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | PROVIDING FHTC 3RD SITE P. HOUSE , B.WALL SINKING BIG DIA T.WELL & LAYING NEW UPVC PIPE LINE WITH RISING MAIN AND OTHER ALLIED WORKS AT PWSS |  |  | VCH/000528/2022-2023 | 355 p | 29/10/2022 | 29/10/2022 | MS SSB CONSTRUCTION CO | 9.13 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | FHTC AT PWSS |  |  | BILL/00679/2022-2023 | BP-882-22-23-P1 | 30/03/2023 | 30/03/2023 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 0.04 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | FUEL BILL SADAR & MTB SUB DIVISION, PHED |  |  | BILL/00642/2022-2023 | BP-793-2022-23 | 18/03/2023 | 18/03/2023 | R.C.BANIK & SONS | 2.5 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | SINKING T/WELL UNDER COB DIVISION, PHED |  |  | BILL/00682/2022-2023 | BP-877-22-23-P1 | 30/03/2023 | 30/03/2023 | MS DD ENTERPRISE | 2.42 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | HIRING VEHICLE FOR AE/SADAR SUB DIVN, PHED |  |  | BILL/00632/2022-2023 | BP-753-2022-23 | 06/03/2023 | 06/03/2023 | PARAUDDIN MIAH | 0.35 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chhagalber Water Supply Scheme | SM/08157 | Retrofitting | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
Total | [13 empty] | 179.21 | 77.07 | 43.01