## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Balakandi Water Supply Scheme | SM/08158 | Retrofitting | PAYMENT TO EE RESOURCE DIV |  |  | VCH/001340/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 10.53 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Balakandi Water Supply Scheme | SM/08158 | Retrofitting | PAYMENT TO RES |  |  | VCH/001345/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 4.13 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Balakandi Water Supply Scheme | SM/08158 | Retrofitting | FHTC |  |  | VCH/000022/2022-2023 | BP-22_23-07 | 13/04/2022 | 13/04/2022 | PARITOSH PANDIT | 4.98 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Balakandi Water Supply Scheme | SM/08158 | Retrofitting | PAyment to res |  |  | VCH/001347/2021-2022 | BP-2021-22-365 | 22/02/2022 | 22/02/2022 | BIJOY ROY | 23.37 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Balakandi Water Supply Scheme | SM/08158 | Retrofitting | traning of operation of mini paramiter |  |  | VCH/001593/2021-2022 | BP-2021_22_410 | 02/03/2022 | 02/03/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 9.33 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Balakandi Water Supply Scheme | SM/08158 | Retrofitting | FHTC |  |  | VCH/001768/2021-2022 | BP-2021_22_454 | 16/03/2022 | 16/03/2022 | TAPAN CHANDA | 1.96 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Balakandi Water Supply Scheme | SM/08158 | Retrofitting | FHTC |  |  | VCH/000085/2022-2023 | BP_22_23_55 | 28/04/2022 | 28/04/2022 | SHYAMAL NATH | 2.91 | 0 | 0 | 0
Total | [13 empty] | 57.22 | 0 | 0