## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | Providing functional House hold tap connection(Unmetered)125 Nos in Chakchaka Piped water Supply Scheme under Cooch Behar Division, P.H.E. Dte. under Jaldhara Programme. |  |  | VCH/001051/2020-2021 | null | 19/03/2021 |  | JHANTU MANDAL | 5.01 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | providing FHTC & OTHER ALLIED WORKS IN THE COMMAND AREA CHAKCHAKA PWSS |  |  | VCH/000255/2021-2022 | null | 08/06/2021 |  | M/S. MANDAL CONSTRUCTION | 10.14 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | Providing FHTC & other allied works in the command area of Chakchaka PWSS under Cooch Behar Division, PHED Part-II |  |  | VCH/000266/2021-2022 | null | 05/07/2021 |  | M/S. MANDAL CONSTRUCTION | 10.14 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | PROVIDING FHTC AT CHAKCHAKA W.S.S. |  |  | VCH/000516/2021-2022 | null | 07/09/2021 |  | M/S. MANDAL CONSTRUCTION | 5.07 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | PROVIDING FHTC AT CHAKCHAKA PWSS (P-D) |  |  | VCH/000517/2021-2022 | null | 07/09/2021 |  | KARTICK CH SEAL | 5.05 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | PROVIDING FHTC FORNAKKATI PWSS |  |  | VCH/000518/2021-2022 | null | 07/09/2021 |  | BISWAJIT GUHA | 12.18 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | FHTC D BAJE JAMA |  |  | VCH/000609/2021-2022 | BP-2021-22-139 | 17/08/2021 |  | DAS ENTERPRISE | 3.2 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | fhtc d baje jama |  |  | VCH/000674/2021-2022 | BP-2021_22_139 | 17/08/2021 |  | DAS ENTERPRISE | 0 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | PIPE LINE IN THE COMMAND AREA INCL. PROVIDING FHTC AT CHAKCHAKA PWSS |  |  | VCH/000759/2021-2022 | null | 30/09/2021 |  | M/S. MANDAL CONSTRUCTION | 28.36 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | FHC CHAKCHAKA |  |  | VCH/000529/2021-2022 | BP-2021-22-88 | 28/07/2021 |  | M/S. MANDAL CONSTRUCTION | 10.14 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | fhtc chakchaka |  |  | VCH/000673/2021-2022 | 156 | 27/08/2021 |  | SANKAR BANIK | 10.13 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | FHTC AT |  |  | VCH/001333/2020-2021 | BP-2021-22-224 | 11/10/2021 |  | SWAPAN KUMAR ROY | 1.94 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | FHTC |  |  | VCH/000977/2021-2022 | BP-2021-22-256 | 30/10/2021 |  | HIRAK CONSTRUCTION | 10.15 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | fhtc |  |  | VCH/001003/2021-2022 | BP-2021-22-273 | 30/10/2021 |  | KHOKAN DAS | 16.28 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | fhtc |  |  | VCH/001009/2021-2022 | BP-2021-22-268 | 30/10/2021 |  | GHOSH AND SAHA CONSTRUCTION | 22.3 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | Providing House connection for CHAKCHAKA PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000335/2021-2022 | 1236/CD | 09/02/2022 | 01/03/2022 | M/S. MANDAL CONSTRUCTION | 10.53 | 0 | 0 | 1
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | FHTC |  |  | VCH/001609/2021-2022 | BP_2021_22_433 | 10/03/2022 |  | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 5.07 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | FHTC |  |  | VCH/001610/2021-2022 | BP_2021_22_434 | 11/03/2022 |  | TISTA LABOUR CO-OP CONT AND CONST SOCIETY LTD | 5 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | COST OF PIPES |  |  | VCH/001750/2021-2022 | BP-2021_22_415 | 04/03/2022 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 7.42 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | fhtc |  |  | VCH/000114/2022-2023 | BP-2022-23-22 | 13/04/2022 |  | ASHIM KUMAR CHAKRABORTY | 0.35 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | Providing 150 nos F.H.T.C. for Chakchaka W.S.S. under Cooch Behar Sadar Sub- Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000105/2022-2023 | 196/SD | 27/06/2022 | 27/07/2022 | M/S. MANDAL CONSTRUCTION | 4.92 | 0 | 0 | 1
22 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | fhtc at chakchaka |  |  | VCH/000673/2022-2023 | 105 | 30/08/2022 |  | M/S. MANDAL CONSTRUCTION | 1.81 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Chakchaka Water Supply Scheme | SM/08159 | Retrofitting | joining of pipe line construction of street stand post and other allied works under Chakchaka PWSS under Cooch Behar Sadar Sub-Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000569/2021-2022 | 721/SD | 18/03/2022 | 02/04/2022 | M/S. MANDAL CONSTRUCTION | 1.3 | 0 | 0 | 1
Total | [13 empty] | 186.48 | 0 | 0