## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | Pipe Line in the Command area incl. Providing House connection at NAZIRGANJ PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000117/2021-2022 | 308/CD | 13/08/2021 | 12/10/2021 | SANKAR CHAKRABORTY | 70.64 | 24.87 | 35.2 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | Providing 140 nos. F.H.T.C. Connection in the command area at NAJIRGANJ P.W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. (Part-D) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000313/2021-2022 | 460/SD | 29/12/2021 | 13/01/2022 | SANKAR CHAKRABORTY | 4.91 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | FHTC AT Krishnapur |  |  | VCH/000932/2021-2022 | BP-2021-22-198 | 11/10/2021 | 11/10/2021 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 5.05 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | fhtc |  |  | VCH/001126/2021-2022 | BP-2021-22-316 | 06/12/2021 | 06/12/2021 | SWAPAN KUMAR ROY | 0 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | Providing house hold connection of drinking water to the house hold of command area under Nazirganj PWSS under Cooch Behar Division, PHED Part-B |  |  | VCH/000942/2020-2021 |  | 18/03/2021 | 18/03/2021 | SANKAR CHAKRABORTY | 32.72 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | PROFIDING FHTC AT BHANDIJALAS PWSS |  |  | VCH/000510/2021-2022 |  | 07/09/2021 | 07/09/2021 | GOUTAM KUMAR DAS | 23.36 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | PROVIDING FHTC NAJIRGANJ |  |  | VCH/000501/2021-2022 | BP-2021_22_48 | 28/07/2021 | 28/07/2021 | SANKAR CHAKRABORTY | 4.1 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | FHTC |  |  | VCH/000972/2021-2022 | BP-2021-22-251 | 28/10/2021 | 28/10/2021 | SANKAR BANIK | 10.09 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | cost of meterial |  |  | VCH/001145/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 2.1 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | Providing house connection of drinking water to the house hold of Command area under NAJIRGANJ PWSS under Cooch Behar Division, PHED PART-A |  |  | VCH/000129/2021-2022 |  | 21/04/2021 | 21/04/2021 | SANKAR CHAKRABORTY | 4.1 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | prov. fhtc at najirganj |  |  | VCH/000238/2021-2022 | 11 | 12/05/2021 | 12/05/2021 | SANKAR CHAKRABORTY | 32.72 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | Providing household tap connection of drinking water to the household of command area under Nalangibari Water Supply Scheme under Mathabhanga Sub Division, P.H.E. Dte. under Jalswapna Prakalpa |  |  | VCH/000703/2021-2022 |  | 13/09/2021 | 13/09/2021 | PARITOSH PANDIT | 5.06 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | Renovation work for the Iron removal filteration plant at Niztaraf PWSS under Mekhliganj Block Jurisdiction under Cooch Behar Division, P.H.E. Dte. |  |  | VCH/000704/2021-2022 |  | 13/09/2021 | 13/09/2021 | GHOSH AND SAHA CONSTRUCTION | 6.91 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | FHTC AT |  |  | VCH/000983/2021-2022 | BP-2021-22-262 | 30/10/2021 | 30/10/2021 | SHYAMAL NATH | 18.01 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | cost of meterial |  |  | VCH/001160/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.08 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Najirganj Water Supply Scheme | SM/08160 | Retrofitting | Providing House connection for SATKURA PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000343/2021-2022 | 1244/CD | 09/02/2022 | 01/03/2022 | ORIENTAL CO OP LABOUR CONTRACT CONSTRUCTION SO | 10.53 | 0 | 0 | 0
Total | [13 empty] | 230.39 | 24.87 | 10.79