## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | Providing functional household tap connection(unmetered)125 nos in Marichbari piped water supply scheme under Cooch behar Division,P.H.E. Dte. under Jaldhara Programme |  |  | VCH/000437/2021-2022 |  | 04/08/2021 | 04/08/2021 | ANIMESH DHAR CHOUDHURY | 5 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | FHTC |  |  | VCH/000979/2021-2022 | BP-2021-22-258 | 30/10/2021 | 30/10/2021 | MS BIDYUT SARKAR | 12.17 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | Laying of pipe line & other allied work related to FHTC under JJM Programme for Marichbari PWSS under Cooch behar Division, P.H.E. Dte. |  |  | VCH/000808/2021-2022 |  | 08/10/2021 | 08/10/2021 | MATARA CONSTRUCTION CO. | 12.17 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | Providing House connection for MARICHBARI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000342/2021-2022 | 1243/CD | 09/02/2022 | 01/03/2022 | MATARA CONSTRUCTION CO. | 10.53 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000051/2021-2022 | 1192/CD | 01/02/2022 | 01/02/2022 | Resource Division | 1.65 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | fhtc |  |  | VCH/001362/2021-2022 | BP-2021-22- 382 | 17/02/2022 | 17/02/2022 | MS SSB CONSTRUCTION CO | 20.63 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | COST OF PIPES |  |  | VCH/001774/2021-2022 | BP-2021-22-415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0.01 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | fhtc bhurkush |  |  | VCH/000230/2022-2023 | BP_77_22_23 | 04/06/2022 | 04/06/2022 | GOUTAM KUMAR DAS | 0.05 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | fhtc |  |  | VCH/001591/2021-2022 | BP-2021_22_412 | 02/03/2022 | 02/03/2022 | SANJAY MANDAL | 5.06 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | fhtc |  |  | VCH/000115/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 0.05 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | FHTC |  |  | VCH/001631/2021-2022 | BP_2021_22_456 | 16/03/2022 | 16/03/2022 | SANKAR CHAKRABORTY | 4.91 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | FHTC |  |  | VCH/001629/2021-2022 | BP_2021_22_453 | 16/03/2022 | 16/03/2022 | SANJAY MANDAL | 4.34 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | FHTC |  |  | VCH/001673/2021-2022 | BP_2021_22_489 | 30/03/2022 | 30/03/2022 | MS SSB CONSTRUCTION CO | 35.63 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | fhtc |  |  | VCH/001370/2021-2022 | BP-2021-22-390 | 22/02/2022 | 22/02/2022 | PARITOSH PANDIT | 5.06 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | FHTC |  |  | VCH/001630/2021-2022 | BP_2021_22_455 | 16/03/2022 | 16/03/2022 | RAJIB CHAKRABORTY | 5.01 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Marichbari Water Supply Scheme | SM/08161 | Retrofitting | HIRING VEWHICLE FOR AE HQ |  |  | BILL/00596/2024-2025 | BP-231 | 01/08/2024 | 01/08/2024 | BHAGWATI BHUJEL | 0.77 | 0 | 0 | 0
Total | [13 empty] | 123.04 | 0 | 0