## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | Providing House connection for PUTIMARI FULESWARI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000057/2021-2022 | 258/CD | 06/08/2021 | 05/09/2021 | GHOSH AND SAHA CONSTRUCTION | 10.15 | 10.15 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | Extension work for providing FHTC 125 nos in Putia Baramasia PWSS |  |  | VCH/000906/2020-2021 |  | 18/03/2021 | 18/03/2021 | NABIN DEBNATH | 5.01 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | fhtc |  |  | VCH/000959/2021-2022 | BP-2021-22-241 | 28/10/2021 | 28/10/2021 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 16.16 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | Fhtc at putimari fulaeswari |  |  | VCH/000241/2021-2022 | 11 | 12/05/2021 | 12/05/2021 | GHOSH AND SAHA CONSTRUCTION | 4.45 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | LAYING PIPELINE & OTHER ALLIED WORKS RELATED TO FHTC UNDER JJM PROGRAMME FOR PUTIMARI PWSS |  |  | VCH/000511/2021-2022 |  | 07/09/2021 | 07/09/2021 | SWAPAN KUMAR ROY | 32.11 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | FHTC A NIJTAF |  |  | VCH/000614/2021-2022 | BP-2021-22-145 | 17/08/2021 | 17/08/2021 | DAS ENTERPRISE | 1.96 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | FHTC AT CHAKCHAKA |  |  | VCH/000329/2021-2022 | 37 | 02/06/2021 | 02/06/2021 | JHANTU MANDAL | 5.01 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | LDS BARA GADAIKHORA |  |  | VCH/000594/2021-2022 | BP-2021-22-124 | 12/08/2021 | 12/08/2021 | BIJOY ROY | 10.73 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | Providing FHTC and other allied works in the command area of Nagarerbari Zone-I PWSS under Cooch Behar Division, PHED, Part-II |  |  | VCH/000911/2020-2021 |  | 18/03/2021 | 18/03/2021 | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 10.06 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | FHTC AT Putimari Phuleswari |  |  | VCH/000956/2021-2022 | BP-2021-22-237 | 28/10/2021 | 28/10/2021 | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 5.13 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | Providing house connection of drinking water to the household of command area under Putimari Phuleswari W/S Scheme(Part-C) of Cooch Behar Division, PHE Dte. under Jaldhara Programme. |  |  | VCH/000944/2020-2021 |  | 18/03/2021 | 18/03/2021 | GHOSH AND SAHA CONSTRUCTION | 4.45 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | Providing functional House hold tap connection(Unmetered)125 Nos in Putia baromasia Piped water Supply Scheme under Mathabhanga Sub Division, P.H.E. Dte. under Jaldhara Programme. |  |  | VCH/000933/2020-2021 |  | 18/03/2021 | 18/03/2021 | NABIN DEBNATH | 5.01 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | fhtc |  |  | VCH/001132/2021-2022 | BP-2021-22-319 | 09/12/2021 | 09/12/2021 | MS BIDYUT SARKAR | 8.92 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | cost of meterial |  |  | VCH/001155/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 2.04 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | fhtc |  |  | VCH/000231/2022-2023 | BP_78_22_23 | 04/06/2022 | 04/06/2022 | MS SURAJIT MAJUMDER | 10.76 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at PUTIMARI FULESWARI W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000536/2021-2022 | 1636/CD | 29/03/2022 | 28/05/2022 | GHOSH AND SAHA CONSTRUCTION | 65.92 | 17.4 | 26.39 | 99
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Putimari Phuleswari Water Supply Scheme | SM/08162 | Retrofitting | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
Total | [13 empty] | 253.56 | 27.55 | 10.86