## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | PROVIDING HFTC UNDER JAMALDAHAT PWSS |  |  | VCH/000768/2021-2022 |  | 30/09/2021 | 30/09/2021 | MS SURAJIT MAJUMDER | 5.06 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | FHTC AT JAMALDAHAT |  |  | VCH/000533/2021-2022 | BP-2021-22-72 | 28/07/2021 | 28/07/2021 | KARTICK CH SEAL | 4.44 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | fhtc |  |  | VCH/000904/2021-2022 | BP-2021-22-167 | 04/10/2021 | 04/10/2021 | GOUTAM KUMAR DAS | 17.25 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | FHTC JAMALDAHAT |  |  | VCH/000577/2021-2022 | BP-2021-22-94 | 28/07/2021 | 28/07/2021 | MS SURAJIT MAJUMDER | 5.03 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | PROVIDING FHTC FOR JAMALDAHAT PWSS |  |  | VCH/000770/2021-2022 |  | 30/09/2021 | 30/09/2021 | MS SURAJIT MAJUMDER | 12.31 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | Providing house connection of drinking water to the household of command area under Jamaldaha hat (Part-A) PWSS under Mathabhanga Sub Division, P.H.E. Dte. Under Jaldhara Programme. |  |  | VCH/000135/2021-2022 |  | 22/04/2021 | 22/04/2021 | KARTICK CH SEAL | 4.44 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | Providing house connection of drinking water to the household of command area under Jamaldaha hat(Part-B) Under Mathabhanga Sub Division, P.H.E. Dte. |  |  | VCH/000282/2021-2022 |  | 06/07/2021 | 06/07/2021 | MS SURAJIT MAJUMDER | 5.03 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | fhtc |  |  | VCH/001131/2021-2022 | BP-2021-22-319 | 09/12/2021 | 09/12/2021 | MS BIDYUT SARKAR | 5.75 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | PROVIDING FHTC UNDER JAMALDAHAT PWSS |  |  | VCH/000726/2021-2022 |  | 22/09/2021 | 22/09/2021 | KARTICK CH SEAL | 0.56 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | Providing functional house hold tap connection (unmetered) 135 nos. in BURABURI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000287/2021-2022 | 322/MTB | 04/01/2022 | 19/01/2022 | PARITOSH PANDIT | 4.98 | 0 | 0 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | Providing functional house hold tap connection within command area of JAMALDAHA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000053/2022-2023 | 45/MTB | 02/05/2022 | 17/05/2022 | MS SURAJIT MAJUMDER | 4.96 | 4.94 | 99.73 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | Providing functional house hold tap connection within command area under Jamaldahat Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000125/2022-2023 | 127/MTB | 23/06/2022 | 08/07/2022 | MS SURAJIT MAJUMDER | 4.81 | 4.81 | 100 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | Providing FHTC Laying of Pipe line incl rising main at 3rd Site at REJ. of JAMALDAH HAT PWSS under JAL JEEVAN MISSION (PART ¿B) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000260/2022-2023 | 773/CD | 05/09/2022 | 04/11/2022 | GOPAL CH.GHOSH | 61.2 | 0 | 0 | 1
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | Sinking of Big Dia Tubewell at 4TH Site of JAMALDAH HAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000194/2022-2023 | 669/CD | 23/08/2022 | 22/10/2022 | MS DD ENTERPRISE | 11.68 | 0 | 0 | 1
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | fhtc |  |  | VCH/001590/2021-2022 | BP-2021_22_411 | 02/03/2022 | 02/03/2022 | M/S. NITYAGOPAL BANIK | 1.06 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | FHTC |  |  | VCH/000107/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 0.5 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | fhtc |  |  | VCH/001369/2021-2022 | BP-2021-22-389 | 22/02/2022 | 22/02/2022 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 4.05 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | fhtc |  |  | VCH/001640/2021-2022 | BP-2021_22_464 | 16/03/2022 | 16/03/2022 | SWAPAN SAHA | 27.34 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | FHTC |  |  | VCH/000152/2022-2023 | BP-22-23-60 | 05/05/2022 | 05/05/2022 | TAPU BANIK | 4.93 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | PRO. FHTC AT JAMALDA HAT |  |  | VCH/000187/2022-2023 | BP_78_22_23 | 04/06/2022 | 04/06/2022 | MS SURAJIT MAJUMDER | 13.84 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | fhtc |  |  | VCH/001354/2021-2022 | BP-2021-22-375 | 17/02/2022 | 17/02/2022 | MANABENDRA DE | 33.98 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | COST OF FUEL WITH FHTC |  |  | VCH/000153/2022-2023 | BP-22-23-75 | 25/05/2022 | 25/05/2022 | ANJALI SERVICE CENTRE | 2.37 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | PROVIDING FHTC AT JAMALDAHAT PWSS |  |  | VCH/001054/2022-2023 | 447 | 30/11/2022 | 30/11/2022 | MS SURAJIT MAJUMDER | 9.41 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | CONST. OF P/HOUSE, B/WALL ETC. AT NAGAR CHANGRABANDHA PWSS |  |  | VCH/001032/2022-2023 | 422 | 14/11/2022 | 14/11/2022 | BISWAJIT GUHA | 2.31 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | fhtc |  |  | VCH/001368/2021-2022 | BP-2021-22-388 | 22/02/2022 | 22/02/2022 | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 37.6 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | FHTC |  |  | VCH/000151/2022-2023 | BP-22-23-64 | 05/05/2022 | 05/05/2022 | TAPASH DAS | 13.46 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | fhtc |  |  | VCH/001385/2021-2022 | BP-2021-22-380 | 17/02/2022 | 17/02/2022 | BIJOY ROY | 2.77 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | FHTC |  |  | VCH/001763/2021-2022 | BP-2021_22_454 | 16/03/2022 | 16/03/2022 | TAPAN CHANDA | 4.32 | 0 | 0 | 0
29 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Jamaldah hat Water Supply Scheme | SM/08163 | Retrofitting | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
Total | [13 empty] | 361.14 | 9.75 | 2.7