## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | Laying of Pipe Line & other allied work related to F.H.T.C. under JJM Programme for CHONGERKHATA KHAGRIBARI PWSS under Cooch Behar Division. PHE Dte. PART A | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000015/2021-2022 | 139/CD | 06/07/2021 | 04/10/2021 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 14.62 | 13.56 | 92.74 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | Fhtc at chonger khata khagrabari |  |  | VCH/000240/2021-2022 | 11 | 12/05/2021 | 12/05/2021 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 5.01 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | Providing House Connection of Drinking water to the househod of command area under Kawardara PWSS under Mathabhanga Sub Division, P.H.E Dte. |  |  | VCH/000701/2021-2022 |  | 13/09/2021 | 13/09/2021 | SEKHAR GHOSAL | 5.01 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | Providing FHTC under Chonger khata Khagribari PWSS |  |  | VCH/000908/2020-2021 |  | 18/03/2021 | 18/03/2021 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 5.01 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | cost metaral |  |  | VCH/001184/2021-2022 | BP-2021-22-318 | 06/12/2021 | 06/12/2021 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 0 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | FHTC AT chonger khata khagrabari |  |  | VCH/000988/2021-2022 | BP-2021-22-266 | 30/10/2021 | 30/10/2021 | KRISHNA GOPAL BASK | 5 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | Providing Rising main of replacement tube well at Head Works Complex and allied works for Chongerkhata Khagribari Piped Water Supply Scheme under Mathabhanga Sub-Division, PHE Dte. |  |  | VCH/001120/2021-2022 | BP-2021-22-327 | 09/12/2021 | 09/12/2021 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 0 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | Providing Rising main of replacement tube well at Head Works Complex and allied works for Chongerkhata Khagribari Piped Water Supply Scheme under Mathabhanga Sub-Division, PHE Dte. |  |  | VCH/001119/2021-2022 | BP-2021-22-327 | 09/12/2021 | 09/12/2021 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 4.83 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | fhtc |  |  | VCH/001597/2021-2022 | BP-2021-22-420 | 11/03/2022 | 11/03/2022 | NABIN DEBNATH | 5.07 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | fhtc |  |  | VCH/001380/2021-2022 | BP-2021-22-403 | 24/02/2022 | 24/02/2022 | PARITOSH PANDIT | 5.09 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | FHTC |  |  | VCH/001764/2021-2022 | BP-2021_22_454 | 16/03/2022 | 16/03/2022 | TAPAN CHANDA | 1.97 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | fhtc |  |  | VCH/001372/2021-2022 | BP-2021-22-392 | 17/02/2022 | 17/02/2022 | BISWAJIT GUHA | 7.05 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | fhtc |  |  | VCH/001371/2021-2022 | BP-2021-22-391 | 22/02/2022 | 22/02/2022 | BISWAJIT GUHA | 10.11 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | fhtc |  |  | VCH/001381/2021-2022 | BP-2021-22-402 | 24/02/2022 | 24/02/2022 | ASHIM KUMAR CHAKRABORTY | 9.49 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | FHTC |  |  | VCH/000087/2022-2023 | BP_22_23_55 | 28/04/2022 | 28/04/2022 | SHYAMAL NATH | 3.07 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | FHTC AT CHUNGERKATHA KHAGRABARI |  |  | VCH/000646/2022-2023 | 212 | 25/08/2022 | 25/08/2022 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 12.75 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | fhtc |  |  | VCH/000096/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 1.21 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of chonger khata khagrabari Water Supply Scheme | SM/08164 | Retrofitting | HIRING VEHICLE FOR EE/CD |  |  | BILL/00482/2024-2025 | BP-206 | 31/07/2024 | 31/07/2024 | SWAPAN KR.SARKAR | 0.34 | 0 | 0 | 0
Total | [13 empty] | 95.63 | 13.56 | 14.18