## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Baro pinjarir Jhar Water Supply Scheme | SM/08165 | Retrofitting | Providing FHTC & Laying P/Line at BARO PINJARERJHAR PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000019/2022-2023 | 35/CD | 07/04/2022 | 22/05/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 26.88 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Baro pinjarir Jhar Water Supply Scheme | SM/08165 | Retrofitting | COST PIPES |  |  | VCH/001753/2021-2022 | BP-2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 4.36 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Baro pinjarir Jhar Water Supply Scheme | SM/08165 | Retrofitting | FHTC |  |  | VCH/001660/2021-2022 | BP_2021_22_479 | 25/03/2022 | 25/03/2022 | TAPAN CHANDA | 17.81 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Baro pinjarir Jhar Water Supply Scheme | SM/08165 | Retrofitting | PAYMENT TO EE RES |  |  | VCH/001339/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 3.06 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Baro pinjarir Jhar Water Supply Scheme | SM/08165 | Retrofitting | PAYMENT TO RES |  |  | VCH/001344/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 46.94 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Baro pinjarir Jhar Water Supply Scheme | SM/08165 | Retrofitting | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000074/2025-2026 | 789/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 69.41 | 0 | 0 | 0
Total | [13 empty] | 168.46 | 0 | 0