## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Requirement of Chemical, Glassware and Instrument of Cooch Behar District Laboratory for NABL Accreditation under Cooch Behar Division P.H.E Dte. | SM/08722 | Support-WQMSP | Supply of different type of Chemicals for all Water Testing Laboratories under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000138/2022-2023 | 524/CD | 14/07/2022 | 29/07/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 2.4 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Requirement of Chemical, Glassware and Instrument of Cooch Behar District Laboratory for NABL Accreditation under Cooch Behar Division P.H.E Dte. | SM/08722 | Support-WQMSP | PROVIDING SERVICE BY ASIGNING RESOURCE PERSON FOR 3 MONTH SUPERVISION OF PREPARATION FOR NABL RECOGNITION FOR CHEMICAL TESTING OF PORTABLE WATER OF SUB DISTWATER QUALITY TESTING LAB. INCL SUPPLY , ISNTALL OF REQUISITES FOR NABL GLAP APPLICATION FOR 11 MANDATORY PARAMETERS FOR SITALKUCHI WATER TESTING LAB. |  |  | VCH/000338/2022-2023 |  | 03/08/2022 | 03/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.18 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Requirement of Chemical, Glassware and Instrument of Cooch Behar District Laboratory for NABL Accreditation under Cooch Behar Division P.H.E Dte. | SM/08722 | Support-WQMSP | PENDING SERVICE BY RESOURCE PERSON NABL CHEMICAL TESTING |  |  | VCH/000577/2022-2023 | 177 | 18/08/2022 | 18/08/2022 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 3.18 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Requirement of Chemical, Glassware and Instrument of Cooch Behar District Laboratory for NABL Accreditation under Cooch Behar Division P.H.E Dte. | SM/08722 | Support-WQMSP | SALRY PAYMENT OF 10 NOS. LABOHRATORY STAFF |  |  | BILL/00549/2023-2024 | BP-40-52 | 19/04/2023 | 19/04/2023 | SECRETARY BOYS RECREATION CLUB DINHATA | 4.85 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Requirement of Chemical, Glassware and Instrument of Cooch Behar District Laboratory for NABL Accreditation under Cooch Behar Division P.H.E Dte. | SM/08722 | Support-WQMSP | HIRING VEHICLE FOR AE/TFG |  |  | BILL/00481/2024-2025 | BP-208 | 31/07/2024 | 31/07/2024 | MATRI ENTERPRISEES | 0.72 | 0 | 0 | 0
Total | [13 empty] | 14.32 | 0 | 0