## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF RAJPUR WATER SUPPLY SCHEME | SM/09292 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Rajpur 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000526/2021-2022 | 1574/CD | 23/03/2022 | 07/04/2022 | MATRI ENTERPRISEES | 2.95 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVINATION OF RAJPUR WATER SUPPLY SCHEME | SM/09292 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of RAJPUR water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. |  |  | ORD/000974/2023-2024 | 2584/NMD-II | 23/08/2023 | 22/09/2023 | SUBHASIS ROY | 10.95 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF RAJPUR WATER SUPPLY SCHEME | SM/09292 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 1954/CD | 24/03/2023 | 24/03/2023 | Resource Division | 54.72 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVINATION OF RAJPUR WATER SUPPLY SCHEME | SM/09292 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RAJPUR (REJU) PH NO-III |  |  | BILL/00156/2023-2024 | BP-2023-24-114 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF RAJPUR WATER SUPPLY SCHEME | SM/09292 | Augmentation | Execution of different works related to RAJPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000078/2023-2024 | 618/CD | 12/07/2023 | 10/09/2023 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 46 | 0 | 0 | 99
6 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF RAJPUR WATER SUPPLY SCHEME | SM/09292 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI/GI Pipe line and other allied works at RAJPUR PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000252/2021-2022 | 901/CD | 24/12/2021 | 22/02/2022 | MATRI ENTERPRISEES | 52.97 | 0 | 0 | 20
Total | [13 empty] | 168.65 | 0 | 0