## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | Providing 100 Nos. F.H.T.C. Connection in the commend area at Chamta W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000545/2021-2022 | 715/SD | 18/03/2022 | 28/03/2022 | RAJU GHOSH | 3.51 | 3.51 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | PAYMENT TO RESOURCE DIV |  |  | VCH/001343/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 40 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | fhtc |  |  | VCH/000109/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 0.51 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | fhtc |  |  | VCH/001594/2021-2022 | BP-2021-22-416 | 11/03/2022 | 11/03/2022 | ASHIM KUMAR CHAKRABORTY | 13.6 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2021-2022 | 1184/CD | 01/02/2022 | 01/02/2022 | Resource Division | 1.1 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 61/CD | 12/04/2022 | 12/04/2022 | Resource Division | 2.2 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 490/CD | 07/07/2022 | 07/07/2022 | Resource Division | 6.16 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT CHAMTA (REJU) PWSS PH NO-III |  |  | BILL/00076/2023-2024 | BP-2023-24-70 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.09 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | SUPPLY OF SLUICE VLVE ETC AT CHAMTA PWSS |  |  | VCH/000877/2022-2023 | 319 | 30/09/2022 | 30/09/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.94 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | Providing FHTC & New HDPE Pipe line and other allied works (PART ¿B) at CHAMTA PWSS under Cooch Behar Division, PHED | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000258/2021-2022 | 907/CD | 24/12/2021 | 22/02/2022 | DIGENDRA CH DEY & SONS | 30.38 | 27.97 | 92.07 | 1
11 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | Providing FHTC Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI/GI Pipe line and other allied works (PART ¿A) at CHAMTA PWSS under Cooch Behar Division, PHED | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000253/2021-2022 | 902/CD | 24/12/2021 | 25/12/2024 | RAJIB CHAKRABORTY | 53.47 | 46.32 | 86.63 | 70
12 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of CHAMTA PWSS under Cooch Behar Division, P.H.E. Dte. | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000084/2022-2023 | 292/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.94 | 0 | 0 | 1
13 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVINATION OF CHAMTA WATER SUPPLY SCHEME | SM/09293 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of CHAMTA water supply scheme, TW no III under NMD-II, PHE Dte.APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000069/2023-2024 | 1226/NMD-II | 30/06/2023 | 04/02/2025 | EMCON | 10.81 | 10.15 | 93.84 | 100
Total | [13 empty] | 172.7 | 87.95 | 50.92