## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Takoamari water supply scheme | SM/09294 | Augmentation | FHTC TAKOMARI |  |  | VCH/000391/2022-2023 | BP-22-23-124 | 11/07/2022 |  | ORIENTAL CO OP LABOUR CONTRACT CONSTRUCTION SO | 19.43 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Takoamari water supply scheme | SM/09294 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of TAKOAMARI PWSS under Cooch Behar Division PHE Dte | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000511/2021-2022 | 1459/CD | 10/03/2022 | 09/04/2022 | AUXILIARY TUBEWELL DRILLERS | 10.7 | 8.78 | 82.08 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvination of Takoamari water supply scheme | SM/09294 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT TAKOAMARI TW NO III |  |  | BILL/00543/2022-2023 | BP-169/22-23 | 29/03/2023 |  | WBSEDCL | 1.06 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvination of Takoamari water supply scheme | SM/09294 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Takoamari water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000029/2023-2024 | 955/NMD-II | 12/05/2023 | 11/06/2023 | MADHAB SAHA | 9.15 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Takoamari water supply scheme | SM/09294 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 19829.63 | 8.78 | 0.04