## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Providing House connection for CHHOTO SAKDAL PWSS under Cooch Behar Division. PHE Dte | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000256/2022-2023 | 740/CD | 27/08/2022 | 11/10/2022 | KANAILAL GOPE | 9.97 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FHTC |  |  | VCH/000035/2022-2023 | BP-22_23-44 | 13/04/2022 | 13/04/2022 | KAJAL KUMAR DE | 1.83 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | SOIL INVESTIGATION AT CHOTO SAKDAL |  |  | VCH/000205/2022-2023 | BP_95_22_23 | 20/06/2022 | 20/06/2022 | A.O BSNL | 1.22 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FHTC |  |  | VCH/000038/2022-2023 | BP_22_23_12 | 13/04/2022 | 13/04/2022 | RED STAR UNEMPLOYED CO -OPARATIVE LABOUR CON.CONS.S LTD. | 29.13 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | COST OF PIPE |  |  | VCH/001639/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 121.81 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FHTC |  |  | VCH/000041/2022-2023 | BP_22_23_14 | 13/04/2022 | 13/04/2022 | MS DD ENTERPRISE | 10.08 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FHTC |  |  | VCH/000045/2022-2023 | BP_22_23_18 | 13/04/2022 | 13/04/2022 | SHYAMAL NATH | 25.18 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FHTC |  |  | VCH/000046/2022-2023 | BP_22_23_19 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 13.06 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FHTC |  |  | VCH/000033/2022-2023 | BP-22_23-41 | 13/04/2022 | 13/04/2022 | NABIN DEBNATH | 37.71 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FHTC |  |  | VCH/000040/2022-2023 | BP_22_23_13 | 13/04/2022 | 13/04/2022 | MATARA CONSTRUCTION CO. | 1.66 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FHTC |  |  | VCH/000083/2022-2023 | BP_22_23_55 | 28/04/2022 | 28/04/2022 | SHYAMAL NATH | 4.37 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FHTC |  |  | VCH/000066/2022-2023 | BP_22_23_52 | 28/04/2022 | 28/04/2022 | NUPUR CHANDRA HALDAR | 5.15 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FHTC |  |  | VCH/000076/2022-2023 | BP_22_23_56 | 28/04/2022 | 28/04/2022 | SHREE RANI SATI ENTERPRISE | 3.46 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Execution of different works related to CHOTO SAKDAL PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000134/2023-2024 | 643_CD | 12/07/2023 | 10/09/2023 | TAPAN CHANDA | 10.79 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Providing FHTC & other allied works at CHHOTO SAKDAL ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000364/2022-2023 | 1017/CD | 29/09/2022 | 29/10/2022 | HIGHLIFE INTERNATIONAL | 9.98 | 0 | 0 | 1
16 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Chhoto Sakdal Water Supply Scheme TW No.-II(Replacement) under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000043/2023-2024 | 1009/NMD-II | 16/05/2023 | 15/06/2023 | GURUKRIPA ENTERPRISE | 8.67 | 0 | 0 | 100
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Chhoto Sakdal 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000517/2021-2022 | 1565/CD | 23/03/2022 | 07/04/2022 | TAPAN CHANDA | 2.98 | 0 | 0 | 1
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 728/CD | 01/12/2021 | 01/12/2021 | Resource Division | 11 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2021-2022 | 1355/CD | 24/02/2022 | 24/02/2022 | Resource Division | 9.83 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2021-2022 | 1183/CD | 01/02/2022 | 01/02/2022 | Resource Division | 1.38 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 206/CD | 27/04/2023 | 27/04/2023 | Resource Division | 0.61 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | UPLOAD CHRGES FOR FHTC |  |  | BILL/00675/2023-2024 | BP-336 | 20/07/2023 | 20/07/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | UPLOAD CHARGES FOR FHTC |  |  | BILL/00674/2023-2024 | BP-340 | 20/07/2023 | 20/07/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
24 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | QUOTATION FOR NSC AT CHOTOSHALDAL TW NO-II |  |  | BILL/01804/2023-2024 | BP-2023-24-361 | 27/09/2023 | 27/09/2023 | WBSEDCL | 3.57 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | HIRING VEHICLE FOR AE/RWS |  |  | BILL/00678/2023-2024 | BP-346 | 20/07/2023 | 20/07/2023 | AJAD HOSSAIN | 0.54 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New HDPE Pipe line and other allied works (PART ¿B) at CHHOTO SAKDAL PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000270/2021-2022 | 949/CD | 31/12/2021 | 31/03/2022 | TAPAN CHANDA | 115.65 | 0 | 0 | 1
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Construction of 200 cum OHR Providing FHTC & New UPVC/DI Pipe line & other allied works (PART ¿A) at CHHOTO SAKDAL PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000278/2021-2022 | 957/CD | 31/12/2021 | 27/10/2022 | MS SSB CONSTRUCTION CO | 182.97 | 0 | 0 | 1
28 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | Providing FHTC and Laying of Pipe line & B/Wall R/Main to CHHOTO SAKDAL PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000224/2022-2023 | 704/CD | 27/08/2022 | 11/10/2022 | MS SSB CONSTRUCTION CO | 60.18 | 0 | 0 | 1
29 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
30 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHHOTA SAKDAL PIPED WATER SUPPLY SCHEME | SM/09296 | Augmentation | FUEL BILL |  |  | BILL/02019/2023-2024 |  | 01/03/2024 | 01/03/2024 | A.O BSNL | 1.78 | 0 | 0 | 0
Total | [13 empty] | 742.24 | 0 | 0