## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | VCH/001601/2021-2022 | BP-2021-22-424 | 10/03/2022 | 10/03/2022 | NORTHE BENGAL CONST CO | 4.98 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | VCH/001678/2021-2022 | BP_2021_22_493 | 31/03/2022 | 31/03/2022 | BISWAJIT GUHA | 4.93 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | VCH/001682/2021-2022 | BP_2021_22_503 | 31/03/2022 | 31/03/2022 | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 10.52 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | SUPPLY OF DELIVERY S VALVE DAUWAGURI |  |  | VCH/000416/2022-2023 | BP-22-23-148 | 26/07/2022 | 26/07/2022 | MS BIDYUT SARKAR | 4.82 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | SUPPLY AND DELIVETY OF JC CUPLING DAWAGURI |  |  | VCH/000417/2022-2023 | BP-22-23-151 | 26/07/2022 | 26/07/2022 | MS BIDYUT SARKAR | 2.48 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | VCH/001681/2021-2022 | BP_2021_22_496 | 31/03/2022 | 31/03/2022 | GOUTAM KUMAR DAS | 5.06 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | VCH/001680/2021-2022 | BP_2021_22_495 | 31/03/2022 | 31/03/2022 | MATARA CONSTRUCTION CO. | 10.53 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | VCH/001677/2021-2022 | BP_2021_22_492 | 31/03/2022 | 31/03/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 12.17 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | PIPE |  |  | VCH/001706/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 1.69 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | VCH/001604/2021-2022 | BP-2021-22-428 | 11/03/2022 | 11/03/2022 | KAJAL KUMAR DE | 0.19 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | VCH/001603/2021-2022 | BP-2021-22-427 | 10/03/2022 | 10/03/2022 | PINAKI SAHA | 4.93 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | VCH/001600/2021-2022 | BP-2021-22-423 | 10/03/2022 | 10/03/2022 | SWAPAN KUMAR ROY | 23.85 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | VCH/001602/2021-2022 | BP-2021-22-425 | 10/03/2022 | 10/03/2022 | SHREE RANI SATI ENTERPRISE | 9.96 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | VCH/001676/2021-2022 | BP_2021_22_491 | 30/03/2022 | 30/03/2022 | ORIENTAL CO OP LABOUR CONTRACT CONSTRUCTION SO | 10.53 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | fhtc |  |  | VCH/001599/2021-2022 | BP-2021-22-422 | 11/03/2022 | 11/03/2022 | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 47.38 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC |  |  | VCH/001675/2021-2022 | BP_2021_22_490 | 30/03/2022 | 30/03/2022 | SWAPAN KUMAR ROY | 8.6 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Laying of pipe line with related works at dawaguri W/S Scheme in connection with JJM Programme. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000650/2022-2023 | 533/SD | 12/12/2022 | 22/12/2022 | RELIANCE UN EMPLOYED ENGINEERS CO OP SOC LTD | 0.95 | 0.95 | 100 | 1
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | FHTC AT PWSS |  |  | BILL/00662/2022-2023 | BP-611-22-23-P | 10/01/2023 | 10/01/2023 | KAJAL KUMAR DE | 1.28 | 0 | 0 | 0
19 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT DAWAGURI (AUG) PH NO I |  |  | BILL/00378/2023-2024 |  | 22/05/2023 | 22/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
20 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT dawaguri (aug) PH NO-I |  |  | BILL/00563/2023-2024 | BP-2023-24-142 | 01/06/2023 | 01/06/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | SUPPLY DIFFT. TYPE OF CHEMICAL FO ALL LABORATORY |  |  | BILL/00572/2023-2024 | BP-94 | 06/05/2023 | 06/05/2023 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 2.4 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Estimate for land registration & other allied works of different new PWSS under Cooch Behar Division, PHE Dte. (Part-B) under JJM. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000871/2022-2023 | 1352/CD | 19/12/2022 | 29/12/2022 | SWAPAN KR.SARKAR | 0.92 | 0 | 0 | 100
23 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Providing FHTC Sinking 250mm X 200mm Big dia Tubewell (PART ¿C) at DAWAGURI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000260/2021-2022 | 909/CD | 24/12/2021 | 24/03/2022 | GHOSH AND SAHA CONSTRUCTION | 11.84 | 11.48 | 96.96 | 1
24 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Providing FHTC Boundary Wall SSPost with soak pit & New HDPE Pipe line and other allied works (PART ¿B) at DAWAGURI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000261/2021-2022 | 910/CD | 24/12/2021 | 22/02/2022 | PARITOSH PANDIT | 32.77 | 27.73 | 84.63 | 1
25 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Dowaguri 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000518/2021-2022 | 1566/CD | 23/03/2022 | 07/04/2022 | GHOSH AND SAHA CONSTRUCTION | 2.98 | 2.78 | 93.41 | 1
26 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Soil investigation work for proposed Over head reservoir of Dawaguri PWSS Scheme under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000580/2021-2022 | 500/SD | 25/01/2022 | 09/02/2022 | CME CONSTRUCTION | 1.22 | 0 | 0 | 100
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Execution of different works related to DAWAGURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000065/2023-2024 | 401/CD | 23/05/2023 | 22/06/2023 | RAHAMAN ENTERPRISE | 9.92 | 9.86 | 99.33 | 95
28 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Name of Work: Execution of different works related to DAWAGURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000259/2023-2024 | 1026/CD | 22/09/2023 | 21/11/2023 | RAHAMAN ENTERPRISE | 12.75 | 10.65 | 83.52 | 84
29 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Constructions of retaining wall & concrete rd to widen the existing damaged rd runs to HWS from NH 31 at DAWAGURI W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000531/2021-2022 | 1631/CD | 29/03/2022 | 28/05/2022 | MS BIDYUT SARKAR | 7.38 | 7.4 | 100.2 | 0
30 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Execution of different works related to DAWAGURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000353/2023-2024 | 1337/CD | 24/11/2023 | 21/07/2024 | MS BIDYUT SARKAR | 35.01 | 33.07 | 94.46 | 49
31 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | HIRING VEHICLE FOR AE/TFG |  |  | BILL/00481/2024-2025 | BP-208 | 31/07/2024 | 31/07/2024 | MATRI ENTERPRISEES | 0.72 | 0 | 0 | 0
32 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dauaguri T.W No I under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001130/2023-2024 | 2872/NMD-II | 17/10/2023 | 16/11/2023 | M/S PALI DEB ENGINEERING | 10.51 | 9.72 | 92.42 | 80
33 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | EXECUTION OF DIFFERENT WORKS (within DAUAGURI area) RELATED TO RAJPUR PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000664/2024-2025 | 92/CD | 17/01/2025 | 18/03/2025 | KRISHNA GOPAL BASAK | 10.69 | 0 | 0 | 0
34 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 10/11/2025 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
35 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000100/2025-2026 | 729/CD | 17/05/2025 | 15/08/2025 | MS BIDYUT SARKAR | 23.91 | 0 | 0 | 0
36 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | Construction of 200 cum OHR Providing FHTC & New UPVC/DI Pipe line & other allied works (PART ¿A) at DAWAGURI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000280/2021-2022 | 959/CD | 31/12/2021 | 14/04/2025 | MS BIDYUT SARKAR | 226.84 | 50.39 | 22.21 | 90
37 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | EXECUTION OF DIFFERENT WORKS (within DAUAGURI area) RELATED TO RAJPUR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000663/2024-2025 | 91/CD | 17/01/2025 | 01/05/2025 | SOMENATH MUKHERJEE | 10.69 | 0 | 0 | 100
38 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DAUAGURI PIPED WATER SUPPLY SCHEME | SM/09297 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000810/2023-2024 | 601/CD | 11/03/2024 | 07/09/2024 | SUBHAS CHANDRA ROY | 5.57 | 0 | 0 | 100
Total | [13 empty] | 640.6 | 164.02 | 25.6