## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Renovation of complete electrical arrangement at Guriahati W/S/S, T.W. No. II in the dist. of Cooch Behar , P.H.E Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000686/2021-2022 | 572/CMSD | 27/08/2021 | 03/09/2021 | DIPA CHHETRI | 0.52 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | SINKING OF T/W, OHR ETC. AT GURIAHATI PWSS |  |  | VCH/001006/2022-2023 | 374 | 23/10/2022 |  | S AND P ENTERPRISE | 72.1 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | FHTC UPLOADING CHARGES FOR COOCH BEHAR DIVISION, PHED |  |  | BILL/00615/2022-2023 | BP-674-2022-23 | 13/02/2023 |  | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | FHTC UPLOADING CHARGES FOR COOCH BEHAR DIVISION, PHED |  |  | BILL/00616/2022-2023 | BP-675-2022-23 | 13/02/2023 |  | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | FHTC AT DHALPAL PWSS |  |  | BILL/01034/2023-2024 | BP-519-P2 | 28/09/2023 |  | ASHIM KUMAR CHAKRABORTY | 19.09 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Construction of 150 cum OHR Providing FHTC Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI Pipe line & other allied works (PART ¿A) at GURIAHATI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000274/2021-2022 | 953/CD | 31/12/2021 | 27/10/2022 | S & P ENTERPRISE | 143.02 | 41.82 | 29.24 | 78
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | CONSTRUCTION OF ohr AND OTHER ALLIED WORKS AT GURIAHATI PWSS |  |  | BILL/01315/2023-2024 | null | 08/12/2023 |  | S & P ENTERPRISE | 14.84 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Execution of different works related to GURIAHATI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000168/2023-2024 | 945/CD | 04/09/2023 | 03/12/2023 | CHAKRABORTY ENTERPRISE | 32.83 | 0 | 0 | 92
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | EXECUTION OF DIFFERENT WOTRK AT GURIAHATI PWSS |  |  | BILL/02000/2023-2024 | BP-1395 | 31/03/2024 |  | M/S T M CONSTRUCTION | 3.67 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 |  | MALAY KR.DEB | 109.82 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Guriahati Water Supply Scheme TW No.- III and IV under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001246/2023-2024 | 2973/NMD-II | 22/11/2023 | 22/12/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 20.23 | 0 | 0 | 70
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Execution of different works related to GURIAHATI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000351/2023-2024 | 1335/CD | 24/11/2023 | 23/01/2024 | RAHAMAN ENTERPRISE | 57.63 | 0 | 0 | 30
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Guriahati 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000521/2021-2022 | 1569/CD | 23/03/2022 | 07/04/2022 | DAFFODIL | 2.95 | 0 | 0 | 1
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitai Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000827/2022-2023 | 2047/CD | 31/03/2023 | 30/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Execution of different works related to AUG. of GURIAHATIZ1 & 2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000407/2023-2024 | 1374/CD | 05/12/2023 | 03/02/2024 | CHAKRABORTY ENTERPRISE | 5.27 | 4.73 | 89.77 | 97
Total | [13 empty] | 484.88 | 47.53 | 9.8