## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Renovation of complete electrical arrangement at Guriahati W/S/S, T.W. No. II in the dist. of Cooch Behar , P.H.E Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000686/2021-2022 | 572/CMSD | 27/08/2021 | 03/09/2021 | DIPA CHHETRI | 0.52 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 108/CD | 26/04/2023 | 26/04/2023 | Resource Division | 9.74 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | FHTC UPLOADING CHARGES FOR COOCH BEHAR DIVISION, PHED |  |  | BILL/00616/2022-2023 | BP-675-2022-23 | 13/02/2023 | 13/02/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | FHTC UPLOADING CHARGES FOR COOCH BEHAR DIVISION, PHED |  |  | BILL/00615/2022-2023 | BP-674-2022-23 | 13/02/2023 | 13/02/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | FHTC AT DHALPAL PWSS |  |  | BILL/01034/2023-2024 | BP-519-P2 | 28/09/2023 | 28/09/2023 | ASHIM KUMAR CHAKRABORTY | 19.09 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Execution of different works related to GURIAHATI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000168/2023-2024 | 945/CD | 04/09/2023 | 03/12/2023 | CHAKRABORTY ENTERPRISE | 32.83 | 0 | 0 | 92
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Guriahati 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000521/2021-2022 | 1569/CD | 23/03/2022 | 07/04/2022 | DAFFODIL | 2.95 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitai Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000827/2022-2023 | 2047/CD | 31/03/2023 | 31/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Execution of different works related to AUG. of GURIAHATIZ1 & 2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000407/2023-2024 | 1374/CD | 05/12/2023 | 03/02/2024 | CHAKRABORTY ENTERPRISE | 5.27 | 0 | 0 | 97
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 1892/CD | 06/11/2024 | 06/11/2024 | Resource Division | 49.28 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 | 22/03/2024 | MALAY KR.DEB | 109.82 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | EXECUTION OF DIFFERENT WOTRK AT GURIAHATI PWSS |  |  | BILL/02000/2023-2024 | BP-1395 | 31/03/2024 | 31/03/2024 | M/S T M CONSTRUCTION | 3.67 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Construction of 150 cum OHR Providing FHTC Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI Pipe line & other allied works (PART ¿A) at GURIAHATI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000274/2021-2022 | 953/CD | 31/12/2021 | 16/08/2025 | S & P ENTERPRISE | 143.02 | 0 | 0 | 78
14 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Guriahati Water Supply Scheme TW No.- III and IV under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001246/2023-2024 | 2973/NMD-II | 22/11/2023 | 22/12/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 20.23 | 0 | 0 | 70
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GURIAHATI PIPED WATER SUPPLY SCHEME | SM/09298 | Augmentation | Execution of different works related to GURIAHATI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000351/2023-2024 | 1335/CD | 24/11/2023 | 19/03/2025 | RAHAMAN ENTERPRISE | 57.63 | 0 | 0 | 30
Total | [13 empty] | 456.96 | 0 | 0