## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | PAYMENT TO RESOURCE DIV |  |  | VCH/001342/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 30 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | FHTC |  |  | VCH/000058/2022-2023 | BP_22_23_31 | 13/04/2022 | 13/04/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 4.98 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | FHTC |  |  | VCH/000067/2022-2023 | BP_22_23_53 | 28/04/2022 | 28/04/2022 | TAPAN CHANDA | 73.12 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | FHTC |  |  | VCH/000057/2022-2023 | BP_22_23_30 | 13/04/2022 | 13/04/2022 | M/S NARAYAN KR. GHOSH | 42.08 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | FHTC |  |  | VCH/000032/2022-2023 | BP-22_23-39 | 13/04/2022 | 13/04/2022 | NANDA DULAL SARKAR | 27.3 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Providing FHTC Pump House SSPost & New UPVC Pipe line and other allied works (PART ¿B) at RAKHALMARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000269/2021-2022 | 948/CD | 31/12/2021 | 31/03/2022 | MATARA CONSTRUCTION CO. | 106.49 | 13.55 | 12.72 | 1
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Soil investigation work for the proposed "Overhead reservoir" of Rakhalmari under Cooch Behar Division P.H.E Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000575/2021-2022 | 498/SD | 25/01/2022 | 09/02/2022 | SHINE ENGINEERING CONSULTANT | 1.22 | 1.22 | 100 | 1
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2021-2022 | 731/CD | 01/12/2021 | 01/12/2021 | Resource Division | 11 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2021-2022 | 1359/CD | 24/02/2022 | 24/02/2022 | Resource Division | 3.17 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2021-2022 | 1185/CD | 01/02/2022 | 01/02/2022 | Resource Division | 1.93 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 207/CD | 27/04/2023 | 27/04/2023 | Resource Division | 8.68 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | exc. of difft. work at chitribari pwss |  |  | BILL/00627/2023-2024 | BP-420-P1 | 25/08/2023 | 25/08/2023 | M/S. NITYAGOPAL BANIK | 9.33 | 0 | 0 | 0
13 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | QUOTATION FOR NSC AT RAKHALMARI PH -II |  |  | BILL/02204/2023-2024 | BP-2023-24-466 | 07/12/2023 | 07/12/2023 | WBSEDCL | 8.15 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | CONST OF OHR AT RAKHALMARI PWS |  |  | BILL/01039/2023-2024 | BP-483 | 18/09/2023 | 18/09/2023 | S & P ENTERPRISE | 38.41 | 0 | 0 | 0
15 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | QUOTATION FOR METER SHIFTING AT RAKHALMARI TW NO-II |  |  | BILL/00540/2022-2023 | BP-159/222-23 | 17/03/2023 | 17/03/2023 | WBSEDCL | 0.07 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | EXECUTION OF DIFFERENT WORKS AT BAJEJAMA CHILAKHANA Z-II PWSS |  |  | BILL/00686/2023-2024 | BP-358 | 28/07/2023 | 28/07/2023 | HARIDAS GHOSH | 13.58 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Preparation of DPR for Augmentation of RAKHALMARI Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000300/2021-2022 | 1095/CD | 10/01/2022 | 31/12/2024 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 3.24 | 3.24 | 100 | 100
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Construction of 150 cum OHR Providing FHTC Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI Pipe line & other allied works (PART ¿A) at RAKHALMARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000275/2021-2022 | 954/CD | 31/12/2021 | 27/10/2022 | S & P ENTERPRISE | 129.84 | 88.33 | 68.03 | 95
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Providing FHTC construction SSPost with soak pit & New HDPE Pipe line and other allied works (PART ¿C) at RAKHALMARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000255/2021-2022 | 904/CD | 24/12/2021 | 22/02/2022 | RED STAR UNEMPLOYED CO -OPARATIVE LABOUR CON.CONS.S LTD. | 30.95 | 0.61 | 1.96 | 0
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Providing FHTC construction SSPost with soak pit & New HDPE Pipe line and other allied works (PART ¿D) at RAKHALMARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000257/2021-2022 | 906/CD | 24/12/2021 | 22/02/2022 | NANDA DULAL GHOSH | 29.14 | 0.54 | 1.86 | 0
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Rakhalmari 2nd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000515/2021-2022 | 1563/CD | 23/03/2022 | 07/04/2022 | DAFFODIL | 2.95 | 2.95 | 100 | 1
22 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGUMENTATION of RAKHALMARI PWSS, TW no .II(REPLACEMENT) in the district of COOCHBEHARunder Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000807/2022-2023 | 407/NMD-II | 24/02/2023 | 26/03/2023 | M/S ANJALI ENTERPRISE | 8.55 | 8.49 | 99.21 | 100
23 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Hiring of Inspection Vehicle for Office of the Assistant Engineer, Coochbehar Mechanical Sub-Division , I.C.W JJM Works under Northern Mechanical Division -II , P.H.E Dte. |  | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000381/2024-2025 | 2474/CMSD | 25/09/2024 | 25/11/2024 | DIPAK SARKAR | 0.69 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Laying Balance portion pipeline & supply of Jeffy coupling & other allied works at RAKHALMARI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000254/2022-2023 | 758/CD | 01/09/2022 | 02/02/2025 | DAFFODIL | 26.91 | 21.53 | 80.02 | 1
25 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF RAKHALMARI PIPED WATER SUPPLY SCHEME | SM/09299 | Augmentation | Execution of different works related to (Within area of AUG. of KALAPANI) RAKHALMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000410/2023-2024 | 1377/CD | 05/12/2023 | 28/01/2025 | SIDHARTHA ROY | 3.9 | 0 | 0 | 96
Total | [13 empty] | 615.67 | 140.45 | 22.81