## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Rasikbill Zone-I 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000522/2021-2022 | 1570/CD | 23/03/2022 | 07/04/2022 | MATARA CONSTRUCTION CO. | 2.98 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | PAYMENT TO RESOUCE DIV |  |  | VCH/001341/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 40 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | fhtc |  |  | VCH/000112/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 0.16 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | OHR AND FHTC AT ANDARAN FULBARI |  |  | VCH/000206/2022-2023 | BP_96_22_23 | 20/06/2022 | 20/06/2022 | GEETA CONSTRUCTION | 146.99 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | HRING VECHICLE |  |  | VCH/000418/2022-2023 | BP-22-23-141 | 15/07/2022 | 15/07/2022 | AJAD HOSSAIN | 0.88 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | SOIL INVESTIGATION AT BALARAMPUR |  |  | VCH/000195/2022-2023 | BP_104_22_23 | 21/06/2022 | 21/06/2022 | MOYTEC | 0.96 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | FHTC |  |  | VCH/001688/2021-2022 | BP_2021_22_500 | 31/03/2022 | 31/03/2022 | SANJAY MANDAL | 9.84 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | SOIL INVESYIGATION |  |  | VCH/000235/2022-2023 | BP_104_22_23 | 21/06/2022 | 21/06/2022 | MOYTEC | 1.19 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Installation of Automatically Controlled Chlorinator (supply departmental) for accurate dosing of chlorine solution at Rampur VI , Santoshpur I & II , Bajejama Chilakhana I, Rasikbill Zone-I P/H No.I under CMSD PHE. Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000932/2020-2021 | 1289/CMSD | 15/03/2021 | 22/03/2021 | PRAGATI CONSTRUCTION COMPANY | 0.52 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Providing FHTC & Construction of Pillar for Pipeline with driving by Sal-bullah & other allied works at RASHIKBILL PWSS under JAL JEEVAN MISSION PART ¿ M | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000295/2022-2023 | 896/CD | 22/09/2022 | 22/10/2022 | KAJAL KUMAR DE | 3.58 | 0 | 0 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | construction of inside drain, pathway chamber with into the HWS of Rasikbill Zone-I PWSS under Tufanganj Sub-Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000570/2021-2022 | 408/TFG | 17/03/2022 | 01/04/2022 | NABIN DEBNATH | 3.88 | 0 | 0 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | construction of Chamber, balance portion work of Rasikbil Zone-IIPWSS under Tufanganj Sub-Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000758/2022-2023 | 84/TFG | 27/04/2022 | 17/05/2022 | NABIN DEBNATH | 1.77 | 0 | 0 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 788/CD | 07/12/2021 | 07/12/2021 | Resource Division | 11.31 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2021-2022 | 1198/CD | 01/02/2022 | 01/02/2022 | Resource Division | 5.87 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 219/CD | 27/04/2023 | 27/04/2023 | Resource Division | 33.04 | 0 | 0 | 0
16 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RASHIKBIL (AUG) TW NO- I,Z-I |  |  | BILL/00025/2023-2024 | BP-2023-24-18 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | HIRING VEHICLE |  |  | VCH/000729/2022-2023 | 266 | 30/09/2022 | 30/09/2022 | SWAPAN KR.SARKAR | 0.18 | 0 | 0 | 0
18 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RASIKBIL PWSS (AUG) Z-II,TW NO-I |  |  | BILL/00026/2023-2024 |  | 11/04/2023 | 11/04/2023 | UJJWAL ROY | 1.06 | 0 | 0 | 0
19 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RASIKBIL PWSS (AUG) Z-II,TW NO-I |  |  | BILL/00110/2023-2024 | BP-2023-24-20 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soakpit Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line and other allied works (PART ¿A) at RASHIKBILL ZONE ¿ I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000241/2021-2022 | 890/CD | 24/12/2021 | 23/04/2022 | MATARA CONSTRUCTION CO. | 253.04 | 0 | 0 | 98
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soakpit Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line and other allied works (PART ¿A) at RASHIKBILL ZONE ¿ I I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000242/2021-2022 | 891/CD | 24/12/2021 | 23/04/2022 | GHOSH AND SAHA CONSTRUCTION | 263.46 | 0 | 0 | 1
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Providing FHTC & New laying UPVC Pipe line construction of Sluice valve chamber & other allied works at RASHIKBILL PWSS under Cooch Behar Division, PHED (PART ¿M) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000251/2021-2022 | 900/CD | 24/12/2021 | 23/04/2022 | KAJAL KUMAR DE | 91.14 | 0 | 0 | 1
23 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Rasikbill Zone-II 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000523/2021-2022 | 1571/CD | 23/03/2022 | 07/04/2022 | GHOSH AND SAHA CONSTRUCTION | 2.98 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Construction of balance portion of inside drain HWS of Rasikbil (Zone-II) WSS under Tufanganj Sub-Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000548/2021-2022 | 409/TFG | 17/03/2022 | 01/04/2022 | NABIN DEBNATH | 3.29 | 0 | 0 | 1
25 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Providing FHTC & other allied works at RASIKBILL ZII PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000371/2022-2023 | 1024/CD | 29/09/2022 | 29/10/2022 | KAJAL KUMAR DE | 9.98 | 0 | 0 | 99
26 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Providing FHTC & other allied works at RASIKBILL ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000372/2022-2023 | 1025/CD | 29/09/2022 | 29/10/2022 | MATARA CONSTRUCTION CO. | 10.02 | 0 | 0 | 100
27 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for AUGUMENTATION of RASIKBIL water supply scheme, TW no I of Zone-I and TW ¿I of Zone-II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000053/2023-2024 | 1134/NMD-II | 08/06/2023 | 08/07/2023 | MADHAB SAHA | 18.6 | 0 | 0 | 100
28 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Rasikbil piped water supply scheme. | SM/09300 | Augmentation | Providing FHTC & other allied works at RASIKBILL ZONE ¿ I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000416/2022-2023 | 1226/CD | 28/11/2022 | 14/02/2026 | HIRAK CONSTRUCTION | 97.91 | 0 | 0 | 90
Total | [13 empty] | 1016.72 | 0 | 0