## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of CHANDAMARI PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000504/2021-2022 | 1452/CD | 10/03/2022 | 09/04/2022 | AUXILIARY TUBEWELL DRILLERS | 10.7 | 9.96 | 93.08 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Providing FHTC with Pipeline laying under Chandamari WSS (Part-B-3) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000129/2022-2023 | 194/SD | 27/06/2022 | 27/07/2022 | NANDA DULAL GHOSH | 4.99 | 4.99 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Providing FHTC with laying of Distribution System under Chandamari W/S Scheme (Part-B-1) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000127/2022-2023 | 192/SD | 27/06/2022 | 27/07/2022 | KANAILAL GOPE | 4.97 | 4.97 | 100 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FHTC with HDPE pipeline at Chandamari WSS, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000123/2022-2023 | 191/SD | 27/06/2022 | 27/07/2022 | KISHORE BOSE | 4.98 | 4.98 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | laying distribution system with FHTC under Chandamari PWSS (Part-B-2) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000124/2022-2023 | 193/SD | 27/06/2022 | 27/07/2022 | GOPAL CH.GHOSH | 4.98 | 4.98 | 100 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Laying distribution system of pipe line with FHTC under Chandamari PWSS PHED. (Part-B-5) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000427/2022-2023 | 195/SD | 27/06/2022 | 27/07/2022 | HIRAK CONSTRUCTION | 4.99 | 4.98 | 99.86 | 1
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Providing FHTC & laying of new pipe line at Chandamari W/S Scheme. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000136/2022-2023 | 190/SD | 27/06/2022 | 27/07/2022 | RAJAT ROY | 5 | 5 | 100 | 1
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Providing FHTC, laying of Pipe line works at CHANDAMARI PWSS under Cooch Behar Division, PHE Dte. PART D1 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000061/2022-2023 | 258/CD | 24/05/2022 | 23/06/2022 | SUBHAJIT DUTTA | 8.17 | 8.17 | 100 | 1
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | New laying of Pipe Line, Providing F.H.T.C. & Other allied works at (Part-P4) CHANDAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000285/2022-2023 | 1044/CD | 29/09/2022 | 28/11/2022 | PRIYANKA MANDAL | 16.57 | 16.54 | 99.8 | 1
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | fhtc |  |  | VCH/000113/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 0.12 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FHTC |  |  | VCH/001645/2021-2022 | BP-2021_22_469 | 17/03/2022 | 17/03/2022 | PARITOSH PANDIT | 4.96 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | BILL |  |  | VCH/001708/2021-2022 | BP_2021_22_426 | 09/03/2022 | 09/03/2022 | QUALITY COOUNCIL OF INDIA NABL | 0.25 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FHTC |  |  | VCH/001659/2021-2022 | BP_2021_22_478 | 25/03/2022 | 25/03/2022 | NARAYAN CHANDRA BANIK | 3.23 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FHTC |  |  | VCH/001616/2021-2022 | BP_2021_22_440 | 11/03/2022 | 11/03/2022 | TAPAN CHANDA | 21.27 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | PAYMENT TO RESOURCE DIV |  |  | VCH/001336/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 30 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FHTC |  |  | VCH/001758/2021-2022 | BP-2021_22_505 | 31/03/2022 | 31/03/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 0.16 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Construction of 250 cum OHR Providing FHTC & New UPVC/DI Pipe line & other allied works (PART ¿A) at CHANDAMARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000277/2021-2022 | 956/CD | 31/12/2021 | 27/10/2022 | GEETA CONSTRUCTION | 263.53 | 255.53 | 96.96 | 1
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Providing FHTC construction SSPost with soak pit & New HDPE Pipe line and other allied works (PART ¿C) at CHANDAMARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000256/2021-2022 | 905/CD | 24/12/2021 | 22/02/2022 | ASHIT KUMAR GHOSH | 29.56 | 28.45 | 96.24 | 0
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Providing FHTC, laying of Pipe line works at CHANDAMARI PWSS under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000191/2022-2023 | 665/CD | 23/08/2022 | 22/10/2022 | SIBAPADA SINGHA ROY | 7.08 | 7.08 | 100 | 1
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Providing FHTC & Construction of Boundary wall, Pumphouse at HW site CHANDAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000238/2022-2023 | 724/CD | 27/08/2022 | 11/10/2022 | GEETA CONSTRUCTION | 31.42 | 24.1 | 76.72 | 1
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Execution of different works related to CHANDAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000747/2022-2023 | 1821/CD | 06/03/2023 | 05/04/2023 | SENGUPTA ENTERPRISE | 7.46 | 7.46 | 100 | 0
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000801/2022-2023 | 1312/CDW | 12/12/2022 | 19/12/2022 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Execution of different works related to CHANDAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000798/2022-2023 | 1849/CD | 14/03/2023 | 13/04/2023 | DAS AND COMPANY | 6.9 | 6.9 | 100 | 0
24 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000802/2022-2023 | 1323/CDW | 14/12/2022 | 21/12/2022 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000805/2022-2023 | 1360/CDW | 21/12/2022 | 28/12/2022 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000803/2022-2023 | 1326/CDW | 15/12/2022 | 22/12/2022 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000800/2022-2023 | 1300/CDW | 09/12/2022 | 16/12/2022 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000804/2022-2023 | 1340/CDW | 19/12/2022 | 26/12/2022 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
29 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Execution of different works related to CHANDAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000062/2023-2024 | 399/CD | 23/05/2023 | 22/06/2023 | BIPASHA MAHANTA BANIK | 9.8 | 9.8 | 99.98 | 100
30 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 729/CD | 01/12/2021 | 01/12/2021 | Resource Division | 11 | 0 | 0 | 0
31 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2021-2022 | 1363/CD | 24/02/2022 | 24/02/2022 | Resource Division | 14.16 | 0 | 0 | 0
32 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2021-2022 | 1178/CD | 01/02/2022 | 01/02/2022 | Resource Division | 1.65 | 0 | 0 | 0
33 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Providing FHTC & other allied works at PWSS under JAL JEEVAN MISSION |  |  | VCH/000851/2022-2023 | 346 P | 25/10/2022 | 25/10/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 0.86 | 0 | 0 | 0
34 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FHTC UPLOADING CHARGES FOR COOCH BEHAR DIVISION, PHED |  |  | BILL/00618/2022-2023 | BP-672-2022-23 | 04/02/2023 | 04/02/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
35 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at P. W.S.S under Cooch Behar Division P.H.E.Dte. |  |  | VCH/000867/2022-2023 | 341 P | 25/10/2022 | 25/10/2022 | NARAYAN CHANDRA BANIK | 2.42 | 0 | 0 | 0
36 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FHTC UPLOADING CHARGES FOR COOCH BEHAR DIVISION, PHED |  |  | BILL/00620/2022-2023 | BP-676-2022-23 | 13/02/2023 | 13/02/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
37 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Quotation for new service connection at Chandamari W/SS TW No- III |  |  | BILL/00010/2022-2023 | BP-98/22-23 | 08/12/2022 | 08/12/2022 | WBSEDCL | 1.06 | 0 | 0 | 0
38 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | SUPPLY ONE MAXI CAB FOR SURVEY IN THE DISTRICT OF COOCH BEHAR |  |  | BILL/00627/2022-2023 | BP-646-2022-23 | 27/02/2023 | 27/02/2023 | PARAKRAM BOSE | 0.79 | 0 | 0 | 0
39 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FUEL BILL FOR E.E. COB DIVISION PHE DTE. FOR THE MONTHE OF AUG 2021 , INVOICE NO. S01324. |  |  | VCH/000547/2022-2023 | 291 | 30/09/2022 | 30/09/2022 | R.C.BANIK & SONS | 3.54 | 0 | 0 | 0
40 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FHTC AT PWSS |  |  | VCH/000932/2022-2023 | 434 P | 30/11/2022 | 30/11/2022 | GHOSH AND SAHA CONSTRUCTION | 3.23 | 0 | 0 | 0
41 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FHTC UPLOADING CHARGES FOR COOCH BEHAR DIVISION, PHED |  |  | BILL/00617/2022-2023 | BP-670-2022-23 | 04/02/2023 | 04/02/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
42 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FHTC UPLOADING CHARGES FOR COOCH BEHAR DIVISION, PHED |  |  | BILL/00619/2022-2023 | BP-671-2022-23 | 04/02/2023 | 04/02/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
43 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Chandamari water supply scheme, TW no IV under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000820/2023-2024 | 2400/NMD-II | 09/08/2023 | 08/09/2023 | HARAGOURI ENTERPRISE | 10.86 | 8.96 | 82.46 | 60
44 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Extension Work order for Hiring of Diesel Vehicle of Bolero Maxi cab for the Office use of Assistant Engineer, Cooch Behar Sadar Sub-Division, PHE Dte. for 6 Months (February 2023 to July 2023) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000737/2022-2023 | 1575/CD | 31/01/2023 | 31/03/2023 | PARAUDDIN MIAH | 1.01 | 0 | 0 | 100
45 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for CHANDAMARI water supply scheme, TW no III (OHR SITE) under JJM under NMD-II, PHE Dte. APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000025/2023-2024 | 932/NMD-II | 10/05/2023 | 09/06/2023 | M/S A.D. ENTERPRISE | 10.92 | 10.86 | 99.44 | 100
46 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | FUEL BILL |  |  | BILL/00564/2024-2025 | BP-213 | 31/07/2024 | 31/07/2024 | R.C BANIK BANIK & SONS | 1.97 | 0 | 0 | 0
47 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | CHARGES FOR PREPARATION OF ESTB. RETURN OFFICE OF THE EE/CD. |  |  | BILL/01084/2024-2025 | BP-219 | 01/08/2024 | 01/08/2024 | PRADIP DHHAR | 1.15 | 0 | 0 | 0
48 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
49 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | supply of fuel for AE/TFG |  |  | BILL/01083/2024-2025 | BP-220 | 31/07/2024 | 31/07/2024 | ANJALI SERVICE CENTRE | 1.53 | 0 | 0 | 0
50 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO CHANDAMARI JIRANPUR ZONE-I (B) & CHILKIRHAT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000536/2024-2025 | 2220/CD | 23/12/2024 | 21/02/2025 | GOUTAM KUMAR DAS | 95.69 | 0 | 0 | 30
51 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHANDAMARI PIPED WATER SUPPLY SCHEME | SM/09302 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000328/2025-2026 | 712/CD | 17/05/2025 | 14/09/2025 | M/S MAHAVIR ENTERPRISE | 7.79 | 0 | 0 | 60
Total | [13 empty] | 716.11 | 423.7 | 59.17