## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line and other allied works (PART ¿B) at DHALPAL PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000271/2021-2022 | 950/CD | 31/12/2021 | 31/03/2022 | NABIN DEBNATH | 126.35 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit & New UPVC Pipe line and other allied works (PART ¿C) at DHALPAL PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000272/2021-2022 | 951/CD | 31/12/2021 | 31/03/2022 | M/S. NITYAGOPAL BANIK | 112.59 | 0 | 0 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Dhalpol Water Supply scheme T/W No.III under NMD-II,PHE.Dte,Cooch Behar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000818/2021-2022 | 173/NMD-II | 22/02/2022 | 24/03/2022 | M/S DE ENGINEERING CONCERN | 2.39 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Constructions of 3rd site Pump House, Boundary Wall at DHALPAL W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000543/2021-2022 | 1643/CD | 29/03/2022 | 28/05/2022 | NABIN DEBNATH | 11.88 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of DHALPAL PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000083/2022-2023 | 291/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Construction footpath, drain & earth filling with some other allied work at 3rd site of Dhalpal PWSS under Tufanganj Sub-Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000279/2022-2023 | 85/TFG | 27/04/2022 | 17/05/2022 | NABIN DEBNATH | 3.04 | 0 | 0 | 1
7 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Dhalpal Water Supply Scheme TW No.-III under NMD-II,PHE Dte Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000825/2021-2022 | 205/NMD-II | 24/02/2022 | 26/03/2022 | KARMAKAR CONSTRUCTION | 7.55 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Shifting pipeline due to widening & strengthening of Tufanganj-Dhalpal-Bhatibari road from 0.00 km to 9.00 km by PWD under Cooch Behar Division. PHE Dte. Part B | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000092/2021-2022 | 270/CD | 06/08/2021 | 20/09/2021 | PARITOSH DUTTA | 18.97 | 0 | 0 | 1
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 1380/CD | 22/12/2022 | 22/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Dhalpal Water supply scheme Near Dhal pal High school Application no. 4002874358 |  |  | VCH/002693/2021-2022 | BP-36/21-22 | 26/03/2022 | 26/03/2022 | WBSEDCL | 0.85 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | PIPE |  |  | VCH/001703/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 7.1 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | SUPPLY CIDI SPL ETC AT DIIRENT OG PWSS |  |  | VCH/000393/2022-2023 | BP-22-23-133 | 12/07/2022 | 12/07/2022 | HIMANGSHU KR.SAHA | 4.24 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Cost of Pipe |  |  | VCH/001637/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 160 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | CONST OHR FHTC DHALPAL |  |  | VCH/000397/2022-2023 | BP-22-23-127 | 11/07/2022 | 11/07/2022 | ASHIM KUMAR CHAKRABORTY | 115.41 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | SHIFTING O/LINE ETC. AT DHALPAL (TFG) |  |  | VCH/000203/2022-2023 | BP_92_22_23 | 21/06/2022 | 21/06/2022 | M/S BADAL CH SAHA | 13.13 | 0 | 0 | 0
16 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Yard lighting arrangement at Pump House No.-I under Dhalpal Water supply scheme Under Northern Mechanical Division-II P.H.E Dte. |  |  | ORD/000643/2021-2022 | 1104/NMD-II | 20/09/2021 | 20/10/2021 | M/S BHOWMIK & CO. | 3.17 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 2nd Site of DHALPAL PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000455/2021-2022 | 1442/CD | 10/03/2022 | 09/04/2022 | MS DD ENTERPRISE | 10.7 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Providing FHTC, Repairing Work of Pump House, New laying of DI Pipe & other allied work related to Rising Main and Pipe Line at DHALPAL PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000223/2022-2023 | 705/CD | 27/08/2022 | 11/10/2022 | ASHIM KUMAR CHAKRABORTY | 30.06 | 0 | 0 | 1
19 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No. I & II under DHALPAL PWSS, PHE Dte. in the district of Coochbehar under NMD-II ,P.H.E Dte | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000537/2021-2022 | 1032/NMD-II | 27/08/2021 | 16/09/2021 | HARAGOURI ENTERPRISE | 1.75 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Shifting pipeline due to widening & strengthening of Tufanganj-Dhalpal-Bhatibari road from 0.00 km to 9.00 km by PWD under Cooch Behar Division. PHE Dte. Part D | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000087/2021-2022 | 211/CD | 26/07/2021 | 24/10/2021 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 8.51 | 0 | 0 | 1
21 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGUMENTATION of Dhalpal PWSS, TW no .II(REPLACEMENT) in the district of COOCHBEHAR under Northern Mechanical Division-II, PHE Dte | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000747/2022-2023 | 118/NMD-II | 13/01/2023 | 12/02/2023 | S.D CONCERN WORKSHOP | 8.61 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2021-2022 | 1204/CD | 01/02/2022 | 01/02/2022 | Resource Division | 2.75 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | VEHICLE BILL |  |  | VCH/000778/2022-2023 | 278 | 30/09/2022 | 30/09/2022 | AJAD HOSSAIN | 0.13 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | FHTC AT CHILKHNA PWSS |  |  | BILL/00689/2023-2024 | BP-330 | 17/07/2023 | 17/07/2023 | ASHIM KUMAR CHAKRABORTY | 9.41 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | SINKING T/W |  |  | VCH/000933/2022-2023 | 294 P | 30/09/2022 | 30/09/2022 | AUXILIARY TUBEWELL DRILLERS | 0.28 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | FUEL CHARGE |  |  | VCH/000930/2022-2023 | 291 P | 30/09/2022 | 30/09/2022 | R.C.BANIK & SONS | 3.12 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | EXECUTION OF DIFFERENT WORKS AT DHALPAL PWSS |  |  | BILL/00668/2023-2024 | BP-261 | 15/07/2023 | 15/07/2023 | ASHIM KUMAR CHAKRABORTY | 1.9 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Providing FHTC & other allied works at DHALPAL PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000420/2022-2023 | 1278/CD | 02/12/2022 | 31/01/2023 | ASHIM KUMAR CHAKRABORTY | 27.83 | 0 | 0 | 1
29 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 1893/CD | 06/11/2024 | 06/11/2024 | Resource Division | 18.48 | 0 | 0 | 0
30 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | PROVIDING INTERNET CONNECTION |  |  | BILL/00601/2024-2025 | BP-236 | 01/08/2024 | 01/08/2024 | BIJOY ROY | 0.18 | 0 | 0 | 0
31 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | PROVIDING INTERNET CONNECTION |  |  | BILL/00600/2024-2025 | BP-235 | 01/08/2024 | 01/08/2024 | BIJOY ROY | 0.1 | 0 | 0 | 0
32 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF DHALPAL PIPED WATER SUPPLY SCHEME | SM/09303 | Augmentation | Charges for load enhancement at Dhalpal PWSS, P/H-II in the dist of Coochbehar. |  |  | BILL/01884/2024-2025 | BP-445/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 0.32 | 0 | 0 | 0
Total | [13 empty] | 777.36 | 0 | 0