## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Creation of Drinking Water source less Anganwadi Centers located Govt. premises in Coochbehar District. | SM/09433 | Anganwadi | Providing House connection for Aunganwadi Center GP Office Educational Institute incl. Mandir & Mashjid at Haldibar & Mekhliganj Block under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000027/2021-2022 | 202/CD | 26/07/2021 | 25/08/2021 | GHOSH AND SAHA CONSTRUCTION | 10.15 | 10.15 | 100 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Creation of Drinking Water source less Anganwadi Centers located Govt. premises in Coochbehar District. | SM/09433 | Anganwadi | Providing house connection for aunganwadi Centre, GP Office, Education Institute, and Health Centre at Mekhliganj Block under Cooch Behar Division, PHE Dte. |  |  | ORD/000149/2021-2022 | 419/CD | 03/09/2021 | 18/10/2021 | MANABENDRA DE | 5.07 | 5.07 | 99.98 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Creation of Drinking Water source less Anganwadi Centers located Govt. premises in Coochbehar District. | SM/09433 | Anganwadi | Providing house connection for aunganwadi Centre, GP Office, Education Institute, and Health Centre at Mathabhanga-I Block under Cooch Behar Division, PHE Dte. |  |  | ORD/000147/2021-2022 | 417/CD | 03/09/2021 | 18/10/2021 | BISWAJIT GUHA | 5.06 | 4.98 | 98.3 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Creation of Drinking Water source less Anganwadi Centers located Govt. premises in Coochbehar District. | SM/09433 | Anganwadi | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000024/2025-2026 | 706/CD | 17/05/2025 | 18/11/2025 | MS SSB CONSTRUCTION CO | 38.34 | 0 | 0 | 30
5 | COOCHBEHAR |  | Coochbehar Division | Creation of Drinking Water source less Anganwadi Centers located Govt. premises in Coochbehar District. | SM/09433 | Anganwadi | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION |  |  | ORD/000049/2025-2026 | 724/CD | 17/05/2025 | 15/08/2025 | AASHIRBAD ENTERPRISE | 83.45 | 0 | 0 | 0
Total | [13 empty] | 142.06 | 20.19 | 14.21