## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | Providing House connection for DAKSHIN BAJEJAMA PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000350/2021-2022 | 1251/CD | 09/02/2022 | 11/03/2022 | DAS ENTERPRISE | 7.04 | 7.04 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | FHTC DAKSHIN BAJE JAMA |  |  | VCH/000412/2022-2023 | BP-22-23-147 | 26/07/2022 |  | DAS ENTERPRISE | 79.32 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | Laying of Pipe line works at Aug. of Dakshin Bajejama PWSS under Cooch Behar Division, PHE Dte. Part C | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000190/2022-2023 | 664/CD | 23/08/2022 | 22/10/2022 | DAS ENTERPRISE | 8.13 | 7.95 | 97.82 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | Providing functional house hold tap connection (FHTC), including Sinking of Big dia T/W, Construction of Pump house, installation of IEP with other allied works in connection with Augmentation work of DAKSHIN BAJEJAMA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. ( Part- B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000419/2021-2022 | 1517/CD | 15/03/2022 | 13/06/2022 | S AND P ENTERPRISE | 123.84 | 39.99 | 32.29 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | FHTC AT PWSS |  |  | BILL/00669/2022-2023 | BP-615-22-23-P | 11/01/2023 |  | SHIBA ENTERPRISE | 1.7 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | FHTC OTHER ALLIED WORKS AT PWSS |  |  | BILL/00673/2022-2023 | BP-585-2022-23 | 10/01/2023 |  | DAS ENTERPRISE | 7.18 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | FHTC AT PWSS |  |  | BILL/00668/2022-2023 | null | 28/12/2022 |  | DAS ENTERPRISE | 7.18 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT DAKSHIN BAJEJAMA TW NO-III,Z-III |  |  | BILL/00086/2023-2024 | BP-2023-24-79 | 15/05/2023 |  | WBSEDCL | 1.05 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | Providing functional house hold tap connection (FHTC), including , Construction of Boundary wall with other allied works in connection with Augmentation work of DAKSHIN BAJEJAMA Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. ( Part- A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000433/2021-2022 | 1528/CD | 15/03/2022 | 13/06/2022 | DAS ENTERPRISE | 122.51 | 22.06 | 18.01 | 100
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | Execution of different works related to DAKSHIN BAJHEJAMA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000799/2022-2023 | 1872/CD | 14/03/2023 | 13/04/2023 | UDAY CHAKI | 5.94 | 4.55 | 76.61 | 100
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Dakshin Bajejama Water Supply Scheme. | SM/09807 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentaion of DAKSHIN BAJEJAMA water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000019/2023-2024 | 914/NMD-II | 05/05/2023 | 04/06/2023 | SUNLIT | 11.04 | 0 | 0 | 80
Total | [13 empty] | 430.63 | 81.59 | 18.95