## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | Providing FHTC & Laying Pipe line & other allied works at KISMAT DASGRAM PWSS under Cooch Behar Division, PHED Part D | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000370/2021-2022 | 1273/CD | 09/02/2022 | 10/04/2022 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 17.04 | 16.57 | 97.24 | 1
2 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 2nd Site of DASGRAM GOBRACHHARA PWSS under Cooch Behar Division PHE Dte. (Replacement Tubewell) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000458/2021-2022 | 1445/CD | 10/03/2022 | 09/04/2022 | MS DD ENTERPRISE | 10.7 | 9.57 | 89.48 | 1
3 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | Sinking of Big Dia Tubewell at KISMAT DASGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000243/2022-2023 | 731/CD | 27/08/2022 | 11/10/2022 | SUBIR GHOSH | 11.68 | 11.64 | 99.69 | 1
4 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | FHTC |  |  | VCH/001686/2021-2022 | BP_2021_22_497 | 30/03/2022 | 30/03/2022 | GOUTAM KUMAR DAS | 4.98 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | PAYMENT TO RESOURCE DIV |  |  | VCH/001335/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 40 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | FHTC |  |  | VCH/001687/2021-2022 | BP_2021_22_505 | 31/03/2022 | 31/03/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.79 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | FHTC |  |  | VCH/001685/2021-2022 | BP_2021_22_499 | 30/03/2022 | 30/03/2022 | MALAY KR.DEB | 20.22 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | Execution of different works related to KISMAT DASGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000031/2023-2024 | 379/CD | 23/05/2023 | 22/07/2023 | SHYAMAL NATH | 24.57 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 784/CD | 07/12/2021 | 07/12/2021 | Resource Division | 11.39 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2021-2022 | 1180/CD | 01/02/2022 | 01/02/2022 | Resource Division | 3.3 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2021-2022 | 1592/CD | 24/03/2022 | 24/03/2022 | Resource Division | 5.49 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT KISAMAT DASGRAM PWSS REJU TW NO III |  |  | BILL/00012/2023-2024 | BP-2023-24-19 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | Providing FHTC & New Laying of Pipe Line and other allied works at KISMAT DASGRAM PWSS under Cooch Behar Division, PHED PART - B | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000375/2021-2022 | 1287/CD | 15/02/2022 | 16/05/2022 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 39.23 | 22.3 | 56.84 | 1
14 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation Kisamat Dasagram water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000071/2023-2024 | 1243/NMD-II | 04/07/2023 | 03/08/2023 | S.D CONCERN WORKSHOP | 10.94 | 10.28 | 93.98 | 100
15 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVINATION OF KISMAT DASGRAM WATER SUPPLY SCHEME | SM/09809 | Augmentation | Hiring of inspection vehicle for office of the Assistant Engineer , Coochbehar Mechanical Sub- Division, I.C.W JJM works under Northern Mechanical Division -II, P.H.E. Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/002124/2023-2024 | 1674/CMSD | 27/03/2024 | 27/05/2024 | DIPAK SARKAR | 0.69 | 0 | 0 | 100
Total | [13 empty] | 206.09 | 70.37 | 34.15