## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Withdrawing of 10 HP submersible pump machinery & installation the same capacityat P/H No. I under Kaminirghat WATER SUPPLY SCHEME in the diast. of Coochbehar under NMD-II, PHE Dte. |  |  | ORD/001043/2021-2022 | 920/CMSD | 21/12/2021 | 28/12/2021 | SUNLIT | 0.23 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Laying of raising main & delivery line connection , Constructions of Head works site Pump & Boundary wall and Other allied works at Kaminirghat under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000373/2021-2022 | 1276/CD | 09/02/2022 | 10/04/2022 | M/S. MANDAL CONSTRUCTION | 22.07 | 21.43 | 97.09 | 98
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | New laying of HDPE/DI pipe line, providing FHTC & other allied works at Kaminirghat (Part- C) PWSS under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000357/2021-2022 | 1257/CD | 09/02/2022 | 10/04/2022 | CHAKRABORTY ENTERPRISE. | 42.1 | 42.08 | 99.97 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | New laying of HDPE/DI pipe line, providing FHTC & other allied works at Kaminirghat (Part- D) PWSS under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000358/2021-2022 | 1258/CD | 09/02/2022 | 10/04/2022 | CHAKRABORTY ENTERPRISE. | 41.02 | 41.02 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | New laying of HDPE/DI pipe line, providing FHTC & other allied works at Kaminirghat (Part- F) PWSS under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000360/2021-2022 | 1263/CD | 09/02/2022 | 26/03/2022 | NARAYAN CHANDRA BANIK | 24.88 | 24.78 | 99.59 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | New laying of HDPE/DI pipe line, providing FHTC & other allied works at Kaminirghat (Part- B) PWSS under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000353/2021-2022 | 1255/CD | 09/02/2022 | 10/04/2022 | ANIMESH DHAR CHOUDHURY | 58.91 | 58.34 | 99.03 | 1
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | New laying of HDPE/DI pipe line, providing FHTC & other allied works at Kaminirghat (Part- E) PWSS under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000359/2021-2022 | 1259/CD | 09/02/2022 | 10/05/2022 | BISWAJIT GUHA | 66 | 59.35 | 89.92 | 1
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | New laying of HDPE/DI pipe line, providing FHTC & other allied works at Kaminirghat (Part- G) PWSS under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000361/2021-2022 | 1264/CD | 09/02/2022 | 26/03/2022 | ORIENTAL CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 26.77 | 26.64 | 99.52 | 60
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Constructions of 350 OHR as per Departmental Design & drawing , New laying of UPVC/DI Pipe Line(PART-A) , Providing F.H.T.C & other allied work at Kaminirghat PWSS under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000431/2021-2022 | 1515/CD | 15/03/2022 | 09/01/2023 | GHOSH AND SAHA CONSTRUCTION | 170.19 | 165.55 | 97.27 | 90
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Providing FHTC and Laying of Pipe line & other allied works related to KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000233/2022-2023 | 721/CD | 27/08/2022 | 11/10/2022 | DAS ENTERPRISE | 21.86 | 21.86 | 100 | 97
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000339/2022-2023 | 992/CD | 29/09/2022 | 29/10/2022 | CHAKRABORTY ENTERPRISE. | 41.04 | 40.97 | 99.83 | 1
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Special repair of pipe line installation of stand post, valve chamber and repairing of Leakage under Kaminirghat WSS PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000280/2022-2023 | 78/SD | 13/05/2022 | 12/06/2022 | CHAKRABORTY ENTERPRISE. | 4.46 | 4.46 | 100 | 1
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Execution of different works related to KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000443/2022-2023 | 1420/CD | 29/12/2022 | 28/01/2023 | M/S A. B. ENTERPRISE | 9.98 | 9.97 | 99.98 | 1
14 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of KAMINIRGHAT Water Supply Scheme TW No.- II (Replacement) in the Dist of Coochbehar under Jal Jeevan Mission under NMD-II PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000706/2022-2023 | 2049/NMD-II | 19/12/2022 | 18/01/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 5.57 | 5.43 | 97.57 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Estimate for land registration & other allied works of different new PWSS under Cooch Behar Division, PHE Dte. (Part-A) under JJM. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000870/2022-2023 | 1343/CD | 19/12/2022 | 29/12/2022 | SWAPAN KR.SARKAR | 0.92 | 0 | 0 | 100
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | PAYMENT TO RESOURCE DIV |  |  | VCH/001334/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 30 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | FHTC AT DIFF. PWSS |  |  | VCH/000762/2022-2023 | 256 | 19/09/2022 | 19/09/2022 | SARKAR CONSTRUCTION | 3.68 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Execution of different works related to KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000788/2022-2023 | 1864/CD | 14/03/2023 | 13/04/2023 | CHAKRABORTY ENTERPRISE. | 26.08 | 25.82 | 99 | 99
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000824/2022-2023 | 2018/CD | 30/03/2023 | 30/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
20 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentaion of KAMINIRGHAT water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001072/2023-2024 | 2760/NMD-II | 04/10/2023 | 03/11/2023 | M/S CHANDRANATH MUKHERJEE | 11.03 | 6.29 | 57.01 | 60
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Name of Work: Execution of different works related to KAMINIRGHAT PWSS under JAL JEEVAN MISSION PART A | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000267/2023-2024 | 1036/CD | 22/09/2023 | 21/11/2023 | KRISHCHAK TRADING PRIVATE LIMITED | 16.58 | 16.58 | 100 | 100
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Name of Work: Execution of different works related to KAMINIRGHAT PWSS under JAL JEEVAN MISSION PART B | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000269/2023-2024 | 1037/CD | 22/09/2023 | 21/11/2023 | RAJAT ROY | 23.43 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Execution of different works related to KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000397/2023-2024 | 1369/CD | 05/12/2023 | 30/09/2024 | KRISHCHAK TRADING PRIVATE LIMITED | 28.84 | 22.54 | 78.14 | 79
24 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Execution of different works related to KAMINIRGHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000347/2023-2024 | 1331/CD | 24/11/2023 | 23/01/2024 | GHOSH AND SAHA CONSTRUCTION | 3.32 | 3.3 | 99.29 | 30
25 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | QUOTATION FOR NSC AT KAMINIRGHAT PH NO III |  |  | BILL/01019/2023-2024 | BP-2023-24-226 | 24/07/2023 | 24/07/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
26 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Quotation for new service connection at Kaminirghat W/SS TW No-II |  |  | BILL/00249/2022-2023 | BP-136/22-23 | 31/01/2023 | 31/01/2023 | WBSEDCL | 1.1 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | FHTC AT PWSS UNDER COB DIVN., PHED |  |  | BILL/00677/2022-2023 | BP-834-22-23-P1 | 30/03/2023 | 30/03/2023 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 0 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | Execution of different works with in CHANDAN CHOWRA & KAMINIRGHAT area related to KAMINIRGHAT PWSS under JAL JEEVAN MISSION PART B | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000077/2024-2025 | 1712/CD | 25/09/2024 | 21/12/2025 | RAJAT ROY | 23.43 | 0 | 0 | 30
29 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | CHARGES FOR SHIFTING OF POLE FOR KAMINIRGHAT PWSS |  |  | BILL/02744/2023-2024 | BP-2023-24-606 | 16/02/2024 | 16/02/2024 | WBSEDCL | 0.82 | 0 | 0 | 0
30 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
31 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | SERVICE CONNECTION CHARGES AT KAMINIR GHAT PH-III |  |  | BILL/00171/2024-2025 | BP-38/24-25 | 26/04/2024 | 26/04/2024 | WBSEDCL | 5.3 | 0 | 0 | 0
32 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KAMINIRGHAT PIPED WATER SUPPLY SCHEME | SM/09810 | Augmentation | SERVICE CONNECTION CHARGES AT KAMINIR GHAT PH-III |  |  | BILL/00172/2024-2025 | BP-37/24-25 | 26/04/2024 | 26/04/2024 | WBSEDCL | 0.92 | 0 | 0 | 0
Total | [13 empty] | 768.3 | 597.41 | 77.76