## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of SALBARI PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000086/2022-2023 | 294/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.93 | 4.93 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of SALBARI PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000506/2021-2022 | 1454/CD | 10/03/2022 | 09/04/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 10.7 | 7.7 | 71.93 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | Quotation for new service connection at Salbari TW No-III ,Application no.4003014783 |  |  | VCH/001457/2022-2023 |  | 18/11/2022 | 18/11/2022 | WBSEDCL | 1.06 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | HIRING VECHILE |  |  | VCH/000401/2022-2023 | BP-22-23-139 | 14/07/2022 | 14/07/2022 | ANIRUDDHA DHAR CHOUDHURY | 0.17 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | FHTC SALBARI |  |  | VCH/000023/2022-2023 | BP-22_23-8 | 13/04/2022 | 13/04/2022 | TAPU BANIK | 28.48 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | FHTC |  |  | VCH/000082/2022-2023 | BP_22_23_56 | 28/04/2022 | 28/04/2022 | SHREE RANI SATI ENTERPRISE | 0.31 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | Quotation for new service connection at SALBARI, P/H no. III, Application no. 4003014783 |  |  | VCH/001467/2022-2023 | BP-90/22-23 | 22/11/2022 | 22/11/2022 | WBSEDCL | 1.06 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | Construction P.House 3rd Site & B/Wall & Providing FHTC New Pipe line & other allied works (Part - A) at SALBARI PWSS under Cooch Behar Division, | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000379/2021-2022 | 1291/CD | 15/02/2022 | 16/05/2022 | TAPU BANIK | 32.47 | 30.88 | 95.1 | 1
9 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SALBARI PWSS, TW no III in the district of COOCHBEHAR under Northern Mechanical Division-II, PHE Dte, ALIPURDUAR. |  |  | ORD/000715/2022-2023 | 2101/NMD-II | 29/12/2022 | 28/01/2023 | S.P ENTERPRISE (SLG) | 10.75 | 10.06 | 93.64 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000034/2025-2026 | 719/CD | 17/05/2025 | 13/11/2025 | AASHIRBAD ENTERPRISE | 50.96 | 0 | 0 | 70
12 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Salbari Water Supply Scheme | SM/09818 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000284/2025-2026 | 793/CD | 23/05/2025 | 21/08/2025 | PALLAB BHAWAL | 30.52 | 0 | 0 | 0
Total | [13 empty] | 227.1 | 53.57 | 23.59