## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Chhatoa water supply scheme | SM/09819 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 1385/CD | 22/12/2022 | 22/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Chhatoa water supply scheme | SM/09819 | Augmentation | FHTC AT CHHATOA |  |  | VCH/000798/2022-2023 | 298 | 30/09/2022 | 30/09/2022 | M/S BADAL CH SAHA | 26.6 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Chhatoa water supply scheme | SM/09819 | Augmentation | Providing FHTC Works, Laying of pipe line culvert crossing due to road construction at CHHATOA W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000541/2021-2022 | 1641/CD | 29/03/2022 | 28/05/2022 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 20.03 | 0 | 0 | 1
4 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvination of Chhatoa water supply scheme | SM/09819 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Chhatoa water supply scheme, TW no III of under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000004/2023-2024 | 774/NMD-II | 06/04/2023 | 06/05/2023 | MAA BHABOTARINE ENTERPRISE | 11.34 | 0 | 0 | 100
5 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvination of Chhatoa water supply scheme | SM/09819 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT CHATOA TW NO III |  |  | BILL/00545/2022-2023 | BP-172/22-23 | 30/03/2023 | 30/03/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Chhatoa water supply scheme | SM/09819 | Augmentation | Providing FHTC & other allied works at CHHATOA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000355/2022-2023 | 3008/CD | 29/09/2022 | 29/10/2022 | AASHIRBAD ENTERPRISE | 9.99 | 0 | 0 | 74
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Chhatoa water supply scheme | SM/09819 | Augmentation | Execution of different works related to CHHATOA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000302/2023-2024 | 956/CD | 04/09/2023 | 03/11/2023 | AYUSH ENTERPRISE | 8.53 | 0 | 0 | 100
Total | [13 empty] | 139.15 | 0 | 0